## Vista
Prepared by: | B.Sadhana
Report Date | 07.12.2023
Company Name | Modi Realty Pocharam LLP
Site | Nilgiri Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial noof item req | Item Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
PO.NO | PO Date | Serial noof item req | Item Description
20230923002 | 24.09.2023 | 1 & 2 | Tiles | Part material Delivered , Balance Collect from SSLLP
20231009035 | 09.10.2023 | 1 | Agro Shade Net | Material Delivered
20231128034 | 28.11.2023 | 1 | MS Round pipe | Material Delivered
20231129025 | 29.11.2023 | 1 to 9 | PVC Material | Material Delivered
20231129026 | 29.11.2023 | 1 to10 | CPVC Material | Collect from SSLLP
20231201022 | 29.11.2023 | 1 to 8 | PVC Material | Collect from Ssllp
20231129027 | 29.11.2023 | 1 to 7 | CPVC Material | Material Delivered
20231129028 | 29.11.2023 | 1 to 11 | Plumbing material | Collect from sslllp
20231129029 | 29.11.2023 | 1 to 5 | Hardware material | Collect from Ssllp
20231129033 | 29.11.2023 | 1 to 6 | Hardware material | Material delivered