## Vista
Prepared by: | B.Sadhana
Report Date | 14.12.2023
Company Name | Modi realty miryalaguda
Site | A V R Gulmohar Homes
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | serial no | Material Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
PO.NO | Po Date | Serial noof item req | Item Description | Purchase Officer - Remarks
20230803047 | 2023-08-03 | 1 | Lift Euipment | Payment Pending
20231123012 | 2023-11-24 | 7 | Sink Cock - 2 nos | Collect from SSLLP