## Vista
Prepared by: | Asha jyothi
Report Date | 2023-12-19
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Under Production
20230428021 | 2023-04-28 | 1 | Electrical | Under Production
20230428022 | 2023-04-28 | 1 | Electrical | Under Production
20230428023 | 2023-04-28 | 1 | Electrical | Under Production
20230428024 | 2023-04-28 | 1 | Electrical | Under Production
20230504030 | 2023-05-04 | 1 | Electrical | Under Production
20230504031 | 2023-05-04 | 1 | Electrical | Under Production
20230505033 | 2023-05-05 | 1 | Electrical | Under Production
20230505028 | 2023-05-05 | 1,2 | Electrical | Under Production
20230505027 | 2023-05-05 | 1 | Electrical | Under Production
20230428027 | 2023-05-05 | 1 | Electrical | Under Production
20230807043 | 2023-08-07 | 1 | Electrical | Under Production
20231021031 | 2023-10-21 | 1 | Tiles | collect part material from ssllp
20231103025 | 03.11.2023 | 1,2,3,4 | MS-Grills | Deliverd
20231103024 | 03.11.2023 | 1,2,3,4 | MS-Grills | Deliverd
20231103023 | 03.11.2023 | 1,2,3,4 | MS-Grills | Deliverd
20231103026 | 03.11.2023 | 1,2,3,4 | MS-Grills | Deliverd
20231115017 | 15.11.2023 | 1 | Plumbing-Loft tank | Deliverd Today
20231201048 | 01.12.2023 | 3 | Tiles | collect material from ssllp
20231201056 | 01.12.2023 | 1,2 | Hardware | collect material from ssllp
20231201049 | 01.12.2023 | 1,2 | Panel doors | Delivered by this week
20231204018 | 04.12.2023 | 1 to 9 | Electrical-wires | Collect material from ssllp
20231209004 | 09.12.2023 | 1 | Hardware-Anchor bolt | Received
20231207019 | 07.12.2023 | 1 to 3 | Channel bracket | Received
20231207014 | 07.12.2023 | 1,2 | Harware-GI | Received
20231214034 | 14.12.2023 | 1 to 9 | Electrical -Wires | Nextweek delivery
20231214033 | 14.12.2023 | 1 to 9 | Electrical -Wires | Received
20231214013 | 14.12.2023 | 1,2 | Chemical -Tile grout | Received