## Vista
Prepared by: | B.Sadhana
Report Date | 22.12.2023
Company Name | Modi Realty Pocharam LLP
Site | Nilgiri Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial noof item req | Item Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
PO.NO | PO Date | Serial noof item req | Item Description | Purchase Officer - Remarks
20230923002 | 24.09.2023 | 1 &2 | Tiles | Collect From SSLLP
20231129029 | 29.11.2023 | 1 to 5 | Hardware material | Material Delivered
20231201022 | 29.11.2023 | 1 | No Return Valve | cancel this PO.
20231206015 | 06.12.2023 | 1 | Tan brown Granite | Balance material collect from SSLLP
20231212014 | 11.12.2023 | 1 | Channel Bracket | Material Delivered
20231216006 | 12.12.2023 | 1&2 | CPVC Material | Material Delivered
20231216005 | 12.12.2023 | 1 | Flush Tank | Material Delivered
20231216004 | 12.12.2023 | 1 | Hardware material | Collect from Supplier
20231216003 | 13.12.2023 | 1 | CPVC Elbow | Material Delivered
20231216023 | 16.12.2023 | 1 | PVC Pipes | Material Delivered