## Vista
Prepared by: | Asha jyothi
Report Date | 2024-01-04
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Under Production
20230428021 | 2023-04-28 | 1 | Electrical | Under Production
20230428022 | 2023-04-28 | 1 | Electrical | Under Production
20230428023 | 2023-04-28 | 1 | Electrical | Under Production
20230428024 | 2023-04-28 | 1 | Electrical | Under Production
20230504030 | 2023-05-04 | 1 | Electrical | Under Production
20230504031 | 2023-05-04 | 1 | Electrical | Under Production
20230505033 | 2023-05-05 | 1 | Electrical | Under Production
20230505028 | 2023-05-05 | 1,2 | Electrical | Under Production
20230505027 | 2023-05-05 | 1 | Electrical | Under Production
20230428027 | 2023-05-05 | 1 | Electrical | Under Production
20230807043 | 2023-08-07 | 1 | Electrical | Under Production
20231021031 | 2023-10-21 | 1 | Tiles | collect part material from ssllp
20231201048 | 2023-12-01 | 1,2,3,4 | Tiles | Delivered
20231201056 | 2023-12-01 | 1,2 | Hardware-Hinges | Delivered
20231201049 | 2023-12-01 | 1,2 | Panel Doors | Delivered
20231222031 | 2023-12-22 | 1 | Granite | Delivered
20231221023 | 2023-12-21 | 1 | Cable tray | Next week delivery
20231222007 | 2023-12-22 | 1 | Plastic cards | Delivered tomorrow
20231223020 | 2023-12-23 | 1 | Plumbing -PVC | Deliverd by this week
20231223030 | 2023-12-23 | 1,2 | Hardware-GI | Delivered Today
20231226023 | 2023-12-23 | 1,2 | Hardware-GI | Delivered Today
20231226020 | 2023-12-26 | 1,2 | Hardware-GI | Delivered Today
20231227027 | 2023-12-27 | 1,2 | Electrical-GI Pole | Delivery after dvance payment
20231227040 | 2023-12-27 | 1,2 | Plumbing-PVC | Delivered Today
20231227039 | 2023-12-27 | 1 | Hardware-GI | Delivered Today