## Vista
Prepared by: | Asha jyothi
Report Date | 2024-01-18
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Under Production
20230428021 | 2023-04-28 | 1 | Electrical | Under Production
20230428022 | 2023-04-28 | 1 | Electrical | Under Production
20230428023 | 2023-04-28 | 1 | Electrical | Under Production
20230428024 | 2023-04-28 | 1 | Electrical | Under Production
20230504030 | 2023-05-04 | 1 | Electrical | Under Production
20230504031 | 2023-05-04 | 1 | Electrical | Under Production
20230505033 | 2023-05-05 | 1 | Electrical | Under Production
20230505028 | 2023-05-05 | 1,2 | Electrical | Under Production
20230505027 | 2023-05-05 | 1 | Electrical | Under Production
20230428027 | 2023-05-05 | 1 | Electrical | Under Production
20230807043 | 2023-08-07 | 1 | Electrical | Under Production
20231227027 | 2023-12-27 | 1,2 | Electrical-GI Poles | Delivered by Today
20231229011 | 2023-12-29 | 5,7 | Electrical wires | Delivered today
20240105042 | 2024-01-05 | 1 | Panel Doors | Next week delivery
20240102001 | 2024-01-02 | 1,2,3 | Tiles | PO Cancelled
20240105033 | 2024-01-05 | 1 | Plumbing | Delivered within 2 days
20240105028 | 2024-01-05 | 1 | Tools | Delivered by Today
20240110021 | 2024-01-10 | 1,2,3,4 | Plumbing-CPVC | Delivered by Today
20240110027 | 2024-01-10 | 15 | Plumbing-PVC | Delivered by Today
20240110025 | 2024-01-10 | 1 | Steel-GI | Delivered by Today
20240110026 | 2024-01-10 | 1,2,3,4,5 | Hardware-GI | Delivered by Today
20240110022 | 2024-01-10 | 1 | Tiles | Material ready collect from SSLLP