## Vista
Prepared by: | S.Jaysudha
Report Date | 2024-01-18
Site | Dr. NRK
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Delivered
20230809037
20230809041 | 2023-08-09 | SD Card | Cancelled by Sunil Sir
20230901009 | 01.09.2023 | Equip: Effulent treatment plant | Under discussion
20230901010 | 01.09.2023 | Equip: Sewage treatment plant | Under discussion
20230513022 | 13.05.23 | Nitobond bonding agent
20231209009 | 09.12.2023 | Manhole set RCC with 4 holes | Size not available in market we are checking
20231212001 | 12.12.2023 | Lap top bags | online purchase.
List of requisitions Where PO/WO is prepared and items have not received at site
Po.No. | Po.date | Item Description | Purchase Officer - Remarks
20231106006 | 06.11.2023 | Puf saddle | Collect from SSLLP GV
20231227034 | 2023-12-27 | Armored cable | Deliver by Tommorrow
20231230020 | 30.12.2023 | Cutting blade | Deliver by Tommorrow