## Vista
Prepared by: | B.Sadhana
Report Date | 19.01.2024
Company Name | Modi Realty Pocharam LLP
Site | Nilgiri Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial noof item req | Item Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
PO.NO | PO Date | Serial noof item req | Item Description | Purchase Officer - Remarks
20231206015 | 06.12.2023 | 1 | Tan Brown Granite | Collect From SSLLP
20231227035 | 27.12.2023 | 1 | Measurement Tape | Next week Delivery
20231228008 | 28.12.2023 | 1&2 | Door Stopper | Collect From SSLLP
20231228007 | 28.12.2023 | 1 | Panel Doors | Collect From SSLLP
20231228009 | 28.12.2023 | 1&2 | Panel Doors | Collect From SSLLP
20240108019 | 08.01.2024 | 1 | Luppam | Collect From SSLLP
20240109020 | 09.01.2024 | 1 | Luppam Patti | Next week Delivery