## Vista
Prepared by: | Asha jyothi
Report Date | 2024-01-24
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Under Production
20230428021 | 2023-04-28 | 1 | Electrical | Under Production
20230428022 | 2023-04-28 | 1 | Electrical | Under Production
20230428023 | 2023-04-28 | 1 | Electrical | Under Production
20230428024 | 2023-04-28 | 1 | Electrical | Under Production
20230504030 | 2023-05-04 | 1 | Electrical | Under Production
20230504031 | 2023-05-04 | 1 | Electrical | Under Production
20230505033 | 2023-05-05 | 1 | Electrical | Under Production
20230505028 | 2023-05-05 | 1,2 | Electrical | Under Production
20230505027 | 2023-05-05 | 1 | Electrical | Under Production
20230428027 | 2023-05-05 | 1 | Electrical | Under Production
20230807043 | 2023-08-07 | 1 | Electrical | Under Production
20231227027 | 2023-12-27 | 1,2 | Electrical-Octogonal poles | Material delivered
20240105042 | 2023-01-05 | 1 | Doors | Collect material from SSLLP
20240105033 | 2023-01-05 | 1 | Plumbing | Material delivered
20240110021 | 2023-01-10 | 1 to 4 | Plumbing-CPVC | Collect part material from ssllp
20240110027 | 2023-01-10 | 15 | Plumbing-PVC | Collect part material from ssllp
20240110022 | 2023-01-10 | 1 | Tiles | Delivered
20240110015 | 2023-01-10 | 1 | Tiles | Delivered
20240110026 | 2023-01-10 | 4 | Anchor bolts | Delivered by Today
20240110016 | 2023-01-11 | 1 | Manhole set | PO Cancelled
20240110018 | 2023-01-11 | 1 | Hardware | Delivered
20240110019 | 2023-01-11 | 1 to 13 | Plumbing | Delivered
20240110020 | 2023-01-11 | 1,2 | Fire &Safety | Delivered
20240110024 | 2023-01-11 | 1,2,3 | Plumbing-PVC | Delivered
20240110017 | 2023-01-11 | 1 to 5 | Plumbing-GI items | Delivered
20240112005 | 2023-01-12 | 1 to 3 | UPVC-Windows | Under fabrication
20240112004 | 2023-01-12 | 1 to 3 | UPVC-Windows | Under fabrication
20240112006 | 2023-01-12 | 1 to 3 | UPVC-Windows | Under fabrication
20240116003 | 2023-01-16 | 1 | Steel-MS Grills | Powder coating under process
20240113028 | 2023-01-16 | 1 | MS-Gazette plate | This week delivery
20240117014 | 2023-01-17 | 1 to 5 | Armored cable | Delivered by Today
20240117013 | 2023-01-17 | 1 to 3 | Armored cable | Delivered by Today