## Vista
Prepared by: | S.Jaysudha
Report Date | 2024-02-23
Site | GV ONE
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
202309010109 | 2023-09-01 | Effluent treatment | Under discussion
20230901010 | 2023-09-01 | Sewage Treatment | Under discussion
20240216005 | 2024-02-16 | Fire hydrant wrapping tape | Po.No.20240216015
List of requisitions Where PO/WO is prepared and items have not received at site
Po.No. | PO.date | Item Description | Purchase Officer - Remarks