## Vista
Prepared by: | S.Jaysudha
Report Date | 01-03-24-2024
Site | Dr. NRK
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Delivered
20230809037
20230809041 | 2023-08-09 | SD Card | Cancelled by Sunil Sir
20230901009 | 01.09.2023 | Equip: Effulent treatment plant | Under discussion
20230901010 | 01.09.2023 | Equip: Sewage treatment plant | Under discussion
20230513022 | 13.05.23 | Nitobond bonding agent
List of requisitions Where PO/WO is prepared and items have not received at site
Po.No. | Po.date | Item Description | Purchase Officer - Remarks
20240217032 | 17.02.24 | Waterproofing liquid | Delivered
20240219023 | 19.02.24 | Spray paint | Delivered