## Vista
Prepared by: | Asha jyothi
Report Date | 2024-03-07
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Part material received
20230428021 | 2023-04-28 | 1 | Electrical | Part material received
20230428022 | 2023-04-28 | 1 | Electrical | Part material received
20230428023 | 2023-04-28 | 1 | Electrical | Part material received
20230428024 | 2023-04-28 | 1 | Electrical | Part material received
20230504030 | 2023-05-04 | 1 | Electrical | Part material received
20230504031 | 2023-05-04 | 1 | Electrical | Part material received
20230505033 | 2023-05-05 | 1 | Electrical | Part material received
20230505028 | 2023-05-05 | 1,2 | Electrical | Part material received
20230505027 | 2023-05-05 | 1 | Electrical | Part material received
20230428027 | 2023-05-05 | 1 | Electrical | Part material received
20230807043 | 2023-08-07 | 1 | Electrical | Part material received
20240112006 | 2024-01-12 | 1 to 3 | UPVC-Windows | Received
20240219012 | 2024-02-19 | 2 to 3 | Hardware-GI | PO Cancelled
20240229031 | 2024-02-29 | 1 | Wall plug fishers | Received
20240229028 | 2024-02-29 | 1 | Hacksaw blade | Received
20240229004 | 2024-03-01 | 1 | Railing | Material Delivery after advance payment
20240229005 | 2024-03-01 | 1 | Railing | Material Delivery after advance payment