## Vista
Prepared by: | Asha jyothi
Report Date | 2024-03-21
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Part material received
20230428021 | 2023-04-28 | 1 | Electrical | Part material received
20230428022 | 2023-04-28 | 1 | Electrical | Part material received
20230428023 | 2023-04-28 | 1 | Electrical | Part material received
20230428024 | 2023-04-28 | 1 | Electrical | Part material received
20230504030 | 2023-05-04 | 1 | Electrical | Part material received
20230504031 | 2023-05-04 | 1 | Electrical | Part material received
20230505033 | 2023-05-05 | 1 | Electrical | Part material received
20230505028 | 2023-05-05 | 1,2 | Electrical | Part material received
20230505027 | 2023-05-05 | 1 | Electrical | Part material received
20230428027 | 2023-05-05 | 1 | Electrical | Part material received
20230807043 | 2023-08-07 | 1 | Electrical | Part material received
20240305009 | 2024-03-05 | 1 | MS Railing | Ready to dispatch
20240305008 | 2024-03-05 | 1 | MS Railing | Ready to dispatch
20240305004 | 2024-03-05 | 1 to 3 | MS Grills | Delivered in this week
20240306017 | 2024-03-06 | 1 | Man hole FRP | Delivered by Tomorrow
20240314037 | 2024-03-14 | 1 | Pump | Partially received
20240315020 | 2024-03-15 | 1 | Plumbing-End cap | Delivered