## BRGV
Prepared by: | Asha jyothi
Report Date | 2024-04-10
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Part material received
20230428021 | 2023-04-28 | 1 | Electrical | Part material received
20230428022 | 2023-04-28 | 1 | Electrical | Part material received
20230428023 | 2023-04-28 | 1 | Electrical | Part material received
20230428024 | 2023-04-28 | 1 | Electrical | Part material received
20230504030 | 2023-05-04 | 1 | Electrical | Part material received
20230504031 | 2023-05-04 | 1 | Electrical | Part material received
20230505033 | 2023-05-05 | 1 | Electrical | Part material received
20230505028 | 2023-05-05 | 1,2 | Electrical | Part material received
20230505027 | 2023-05-05 | 1 | Electrical | Part material received
20230428027 | 2023-05-05 | 1 | Electrical | Part material received
20230807043 | 2023-08-07 | 1 | Electrical | Part material received
20240328014 | 2024-03-28 | 1 | Stationery | Delivered Tomorrow
20240330004 | 2024-03-30 | 3 | Sanitary | No stock at MHPL@ Rampally
20240402001 | 2024-04-02 | 1 | Granite adhesive | Next week delivery
20240403033 | 2024-04-03 | 1 | Armored cable | Next week delivery
20240403009 | 2024-04-03 | 1 | Al Service wire | Delivered
20240403008 | 2024-04-03 | 1 | Plumbing-CPVC Clamp | Delivered
20240403006 | 2024-04-03 | 1 | Bakelite stripconnector | Next week delivery
20240404025 | 2024-04-05 | 1 | Plumbing-CPVC Clamp | Delivered Tomorrow