## BRGV
Prepared by: | Asha jyothi
Report Date | 2024-04-24
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
20240417003 | 2024-04-17 | 1 to 3 | Electrical | Catalouge required
List of requisitions Where PO/WO is prepared and items have not received at site
PO No | PO Date | Serial no of item in PO | Material Descscription | Purchase Officer - Remarks
20240403033 | 2024-04-03 | 1 | Armoured cable | Delivered
20240404025 | 2024-04-05 | 1 | CPVC Clamps | No stock at MHPL
20240407002 | 2024-04-07 | 1 | Electrical- Starter | Delivered
20240407001 | 2024-04-08 | 1 | Armoured cable-3 core | Delivered
20240413002 | 2024-04-13 | 1,2 | FRP Manhole set | Delivered by Tomorrow
20240415005 | 2024-04-15 | 1 | Electrical-GI Strip | Delivered
20240415031 | 2024-04-16 | 1,2 | L-Angle & MS Round pipe | Delivered
20240417008 | 2024-04-17 | 6 | Shower Arm | Delivered by this week
20240417024 | 2024-04-17 | 1 to 7 | Consumables | Delivered