## Vista
Prepared by: | B.Sadhana
Report Date | 11.05.2024
Company Name | Modi realty miryalaguda
Site | A V R Gulmohar Homes
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | serial no | Material Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
NILL | NILL
List of requisitions Where PO/WO is prepared and items have not received at site
PO.NO | Po Date | Serial noof item req | Item Description | Purchase Officer - Remarks
20240503005 | 03.-05-2024 | 1 | Electrical | Collect from MHPL
20240429043 | 2024-04-29 | 1 to 4 | Plumbing | Collect from MHPL
20240429036 | 2024-04-29 | 1 to 3 | Plumbing | Collect from MHPL
20240422047 | 2024-04-15 | 1 | Electrical | Collect from MHPL
20240420020 | 2024-04-20 | 1 | Plumbing | Collect from Praful Sanitary