## Vista
Prepared by: | B.Sadhana
Report Date | 21.02.2024
Company Name | MMRK-LLP
Site | GHT
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial noof item req | Item Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
PO No | PO Date | Serial no of item req | Item Description
20240201006 | 01.02.2024 | 1 | GI -Octagonal Pole | Next Week Delivery
20240208021 | 08.02.2024 | 1 to 3 | Floor Paints | Material Delivered
20240207051 | 07.02.2024 | 1 | Tan brown Granite | Collect from SSLLP
20240212021 | 12.02.2024 | 1,2 | Floor Tiles | Material Delivered
20240213036 | 13.02.2024 | 1 to 5 | UPVC Windows | Next Week Delivery