## ghmc park mes
MEASURMENT SHEET
Company Name : |  | MMR - Kowkur LLP
Project : |  | GHT
Work Description: |  | GHMC Park civil work estimation
Prepared BY |  | A Suresh
Name of the Contractor |  | Home line infra
Date : |  | 25.02.2020
|  |  | A | B | C | D | E=Ax B x C x D | F | G= Sum of E | Remarks
S.No. | Item head | Item Desscription | Length | Width | Hight | Nos. | Quantity | Units | Item HeadTotal
1 | Pcc
a) |  | Soack pit wall
|  | North wall | 92 | 2 | 1 | 1 | 184 | Sft
|  | South wall | 92 | 2 | 1 | 1 | 184 | Sft
|  | East wall | 158 | 2 | 1 | 1 | 316 | Sft
|  | west wall | 158 | 2 | 1 | 1 | 316 | Sft
[8 empty] | Sft | 1000
b) | PCC | Land scap wall
|  | North wall | 92.16 | 2 | 1 | 1 | 184.32 | Sft
|  | South wall | 79 | 2 | 1 | 1 | 158 | Sft
|  | East wall | 140 | 2 | 1 | 1 | 280 | Sft
|  | west wall | 110 | 2 | 1 | 1 | 220 | Sft
[8 empty] | Sft | 842.32
c) | Pcc | Driway wall
|  | North wall | 76 | 2 | 1 | 1 | 152 | Sft
|  | South wall | 67 | 2 | 1 | 1 | 134 | Sft
|  | East wall | 122 | 2 | 1 | 1 | 244 | Sft
|  | west wall | 99 | 2 | 1 | 1 | 198 | Sft
|  | Partitation wall | 62 | 2 | 1 | 2 | 248 | Sft | 976
2 | 6 '' Wall | Soack pit wall
|  | North wall | 92 | 1 | 2 | 1 | 184 | Sft
|  | South wall | 92 | 1 | 2 | 1 | 184 | Sft
|  | East wall | 158 | 1 | 2 | 1 | 316 | Sft
|  | west wall | 158 | 1 | 2 | 1 | 316 | Sft
[8 empty] | Sft | 1000
Land scap wall
|  | North wall | 92.16 | 1 | 2 | 1 | 184.32 | Sft
|  | South wall | 79 | 1 | 2 | 1 | 158 | Sft
|  | East wall | 140 | 1 | 2 | 1 | 280 | Sft
|  | west wall | 110 | 1 | 2 | 1 | 220 | Sft
[8 empty] | Sft | 842.32
Driway wall
|  | North wall | 76 | 1 | 2 | 1 | 152 | Sft
|  | South wall | 67 | 1 | 2 | 1 | 134 | Sft
|  | East wall | 120 | 1 | 2 | 1 | 240 | Sft
|  | west wall | 93 | 1 | 2 | 1 | 186 | Sft
[8 empty] | Sft | 712
| Partitation wall | Children play area | 62 | 1 | 2 | 2 | 248 | Sft
|  | Land scap area | 62 | 1 | 2 | 1 | 124 | Sft
[8 empty] | Sft | 372
3 | Plastring wall
Soack pit wall
|  | North wall | 92.16 | 1 | 1.83 | 1 | 168.6528 | Sft
|  | South wall | 92 | 1 | 1.83 | 1 | 168.36 | Sft
|  | East wall | 158 | 1 | 1.83 | 1 | 289.14 | Sft
|  | west wall | 158 | 1 | 1.83 | 1 | 289.14 | Sft
[8 empty] | Sft | 915.2928
Land scap wall
|  | North wall | 92.16 | 1 | 1.83 | 1 | 168.6528 | Sft
|  | South wall | 79 | 1 | 1.83 | 1 | 144.57 | Sft
|  | East wall | 140 | 1 | 1.83 | 1 | 256.2 | Sft
|  | west wall | 110 | 1 | 1.83 | 1 | 201.3 | Sft
[8 empty] | Sft | 770.7228
Driway wall
|  | North wall | 76 | 1 | 1.83 | 1 | 139.08 | Sft
|  | South wall | 67 | 1 | 1.83 | 1 | 122.61 | Sft
|  | East wall | 120 | 1 | 1.83 | 1 | 219.6 | Sft
|  | west wall | 93 | 1 | 1.83 | 1 | 170.19 | Sft
[8 empty] | Sft | 651.48
| Partitation wall | Children play area | 62 | 1 | 1.83 | 1 | 113.46 | Sft
|  | Land sxap area | 62 | 1 | 1.83 | 1 | 113.46 | Sft
[8 empty] | Sft | 226.92
4 | Compound wall | East side wall | 162 | 1 | 4 | 1 | 648 | Sft
| 4'' wall with 9'' brick piller | [6 empty] | Sft | 648
|  | Plastring wall | 162 | 1 | 4.33 | 2 | 1402.92 | Sft
[8 empty] | Sft | 1402.92
5 | North side | CRS Wall | 97 | 1.5 | 2.5 | 1 | 242.5 | Sft | 242.5
| compound wall | plinth beam | 97 | 1 | 1 | 1 | 97 | Sft | 97
|  | Columns | 1 | 1 | 5.5 | 1 | 9 | Nos | 9
|  | 4'' brick work | 84.5 | 1 | 3 | 2 | 507 | Sft | 507
|  | Plastring wall | 84.5 | 1 | 6.34 | 1 | 535.73 | Sft | 535.73
|  | basement plastring | 84.5 | 1 | 5 | 1 | 422.5 | Sft | 422.5
|  | Columns plastring | 3 | 1 | 5.5 | 9 | 148.5 | Sft | 148.5
|  | 1/2'' patti | 84.5 | 1 | 1 | 2 | 169 | Rft | 84.5
|  | Staircase brick work | 6.5 | 1 | 1 | 5 | 32.5 | Sft | 32.5
|  | raiser | 6.5 | 0.5 | 1 | 5 | 16.25 | Sft | 16.25
|  | Plastring | 6.5 | 1 | 1 | 5 | 32.5 | Sft | 32.5
|  |  | 6.5 | 0.5 | 1 | 5 | 16.25 | Sft | 16.25
|  | Column - 0 | 1 | 1 | 1 | 9 | 9 | Nos | 9

## ghmc park est
ESTIMATE SHEET
Company Name : |  | MMR - Kowkur LLP
Project : |  | GHT |  |  |  |  | work done from date
Work Description: |  | GHMC Park civil work estimation |  |  |  |  | work done to date
Prepared BY |  | A Suresh |  |  |  |  | Approved By:
Name of the Contractor |  | Home line infra |  |  |  |  | Sign :
Date : |  | 25.02.202020
contractor
S.No | Item Head | Item Description | Quantity | Units | Rate | Amount | Item Head Total | Asking Rate | Amount | Remarks
1 | Pcc work | Soack pit wall | 1000 | Sft | 5 | 5000 |  | 6 | 6000
|  | Land scap wall | 842.32 | Sft | 5 | 4211.6 |  | 6 | 5053.92
|  | Driway wall | 976 | Sft | 5 | 4880 |  | 6 | 5856
|  | Partitation wall | 372 | Sft | 5 | 1860 |  | 6 | 2232
|  |  | Subtotal A |  |  | 15951.6 |  |  | 19141.92
2 | 6'' wall | Soack pit wall | 1000 | Sft | 10 | 10000 |  | 13 | 13000
|  | Land scap wall | 842.32 | Sft | 10 | 8423.2 |  | 13 | 10950.16
|  | Driway wall | 842.32 | Sft | 10 | 8423.2 |  | 13 | 10950.16
|  | Partitation wall | 372 | Sft | 10 | 3720 |  | 13 | 4836
|  |  | Subtotal B |  |  | 30566.4 |  |  | 39736.32
3 | Plastring wall | Soack pit wall | 915.2928 | Sft | 12 | 10983.5136 |  | 15 | 13729.392
|  | Land scap wall | 770.7228 | Sft | 12 | 9248.6736 |  | 15 | 11560.842
|  | Driway wall | 651.48 | Sft | 12 | 7817.76 |  | 15 | 9772.2
|  | Partitation wall | 226.92 | Sft | 12 | 2723.04 |  | 15 | 3403.8
|  |  | Subtotal C |  |  | 30772.9872 |  |  | 38466.234
4 | Compound wall | 4 '' brick wall | 648 | Sft | 10 | 6480 |  | 13 | 8424
|  | Plastring wal | 1402.92 | Sft | 12 | 16835.04 |  | 15 | 21043.8
|  |  | Subtotal D |  |  | 23315.04 |  |  | 29467.8
5 | North side | CRS Wall | 242.5 |  | 18 | 4365 |  | 18 | 4365
| compound wall | plinth beam | 97 |  | 250 | 24250 |  | 250 | 24250
|  | Columns | 9 |  | 2150 | 19350 |  | 2150 | 19350
|  | 4'' brick work | 507 |  | 10 | 5070 |  | 10 | 5070
|  | Plastring wall | 535.73 |  | 12 | 6428.76 |  | 12 | 6428.76
|  | basement plastring | 422.5 |  | 12 | 5070 |  | 12 | 5070
|  | Columns plastring | 148.5 |  | 12 | 1782 |  | 12 | 1782
|  | 1/2'' patti | 84.5 |  | 15 | 1267.5 |  | 15 | 1267.5
|  | Staircase brick work | 32.5 |  | 12 | 390 |  | 12 | 390
|  | raiser | 16.25 |  | 12 | 195 |  | 12 | 195
|  | Plastring | 32.5 |  | 12 | 390 |  | 12 | 390
|  |  | 16.25 |  | 12 | 195 |  | 12 | 195
|  | Column - 0 | 9 |  | 1173 | 10557 |  | 1173 | 10557
|  |  | Subtotal E |  |  | 79310.26 |  |  | 79310.26
|  |  | Total Amount ( a+b+c+d+e) |  |  | 179916.29 | 179916.2872 |  | 206122.53

## compound wall mes
MEASURMENT SHEET
Company Name : |  | MMR - Kowkur LLP
Project : |  | GHT
Work Description: |  | Compound wall work done measerment detail
Prepared BY |  | A Suresh
Name of the Contractor |  | Home line infra
Date : |  | 03.03.3030
|  |  | A | B | C | D | E=Ax B x C x D | F | G= Sum of E
S.No. | Item head | Item Desscription | Length | Width | Hight | Nos. | Quantity | Units | Item HeadTotal
1 | Compoundwall | Excavation | 99 | 1 | 1 | 1 | 99 | Nos | 99
|  | Footings | 99 | 1 | 1 | 1 | 99 | Nos | 99
|  | Column no -0 | 99 | 1 | 1 | 1 | 99 | Nos | 99
|  | Column no -1 | 99 | 1 | 1 | 1 | 99 | Nos | 99
| More than 2' to 4' | Column no - 0a | 58 | 1 | 1 | 1 | 58 | Nos | 58
|  | Plinth beam | 1460 | 1 | 1 | 1 | 1460 | Rft | 1460
|  | 4'' Brick wall | 1362 | 1 | 5 | 1 | 6810 | Sft | 6810
| Plastring | Plinth beam | 1362 | 1 | 1.664 | 1 | 2266.368 | Sft | 2266.368
|  | Brick wall | 1386 | 1 | 5.34 | 1 | 7401.24 | Sft | 7401.24
|  | RCC Piller | 3 | 1 | 5.5 | 99 | 1633.5 | Sft | 1633.5
| compound wall | Road side | 438.25 | 1 | 5 | 1 | 2191.25 | Sft | 2191.25
| Type 1 wall | Bottom compound wall | 460 | 1 | 3 | 1 | 1380 | Sft | 1380
|  |  | 23 | 1 | 4 | 1 | 92 | Sft | 92
|  | Plinth beam out side area | 460 | 1 | 1.16 | 1 | 533.6 | Sft | 533.6
[8 empty] | Sft | 15497.958
|  | Patti | 2164 | 1 | 1 | 1 | 2164 | Rft | 2164
ESTIMATE SHEET
Company Name : |  | South wall
Project : |  | East wall |  |  |  |  | work done from date
Work Description: |  | Compound wall work done measerment detail |  |  |  |  | work done to date
Prepared BY |  | A Suresh |  |  |  |  | Approved By:
Name of the Contractor |  | Home line infra |  |  |  |  | Sign :
Date : |  | 03.03.2020
S.No | Item Head | Item Description | Quantity | Units | Rate | Amount | Item Head Total | Remarks
1 | compound wall | Excavation | 99 | Nos | 475 | 47025
|  | Footings | 99 | Nos | 1850 | 183150
|  | Column no -0 | 99 | Nos | 800 | 79200
|  | Column no -1 | 99 | Nos | 1350 | 133650
|  | Column no - 0a | 58 | Nos | 1600 | 92800
|  | Plinth beam | 1460 | rft | 250 | 365000
|  | 4'' Brick wall | 7401 | sft | 45 | 333045
|  | Plastring | 15497 | sft | 25 | 387425
|  | Patti | 2164 | Rft | 17 | 36788
1658083

## compound wall est
ESTIMATE SHEET
Company Name : |  | MMR - Kowkur LLP
Project : |  | GHT |  |  |  |  | work done from date
Work Description: |  | Compound wall work done measerment detail |  |  |  |  | work done to date
Prepared BY |  | A Suresh |  |  |  |  | Approved By:
Name of the Contractor |  | Home line infra |  |  |  |  | Sign :
Date : |  | 03.03.2020
S.No | Item Head | Item Description | Quantity | Units | Rate | Amount | Item Head Total | Remarks
1 | compound wall | Excavation | 99 | Nos | 475 | 47025
|  | Footings | 99 | Nos | 1850 | 183150
|  | Column no -0 | 99 | Nos | 800 | 79200
|  | Column no -1 | 99 | Nos | 1350 | 133650
|  | Column no - 0a | 58 | Nos | 1600 | 92800
|  | Plinth beam | 1460 | rft | 250 | 365000
|  | 4'' Brick wall | 7401 | sft | 45 | 333045
|  | Plastring | 15497 | sft | 25 | 387425
|  | Patti | 2164 | Rft | 17 | 36788
1658083