## Anx - D - Milestone report
Annexure - D - send weekly
Mile stone report for CR-
Company name: |  |  |  | Villa Orchids
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 2020-07-06
Note: | Prepare the statement for all the villas in the project.
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Completion of plinth | Completion of RCC | Completion of brickwork and plastering | Completion of stage I | Completion of stage II | Completion of stage III | Completion of stage IV | Date of physical posession
1 | 8 | 3 bhk | 1940 | 2018-01-16 | 2018-07-05 | 2018-12-31 | 2019-07-04 | 2019-07-08 | 2019-09-10 | 2019-12-14
2 | 9 | 3 bhk | 1940 | 2018-10-20 | 2018-04-30 | 2018-10-15 | 2019-01-03 | 2019-04-02 | 2019-07-04 | 2019-11-10
3 | 10 | 3 bhk | 1940 | 2018-11-27 | 2018-05-04 | 2018-10-31 | 2019-01-25 | 2019-03-10 | 2019-08-10 | 2019-11-22 | 2019-12-02 | 2019-12-11
4 | 11 | 3 bhk | 1940 | 2018-01-09 | 2018-05-08 | 2019-02-15 | 2019-12-01 | 06.01.2020 | 2020-01-18
5 | 12 | 3 bhk | 1940 | 2018-01-09 | 2018-04-30 | 2019-06-01 | 2020-01-26 | 2020-03-07 | 2020-06-22
6 | 13 | 3 bhk | 1940 | 2018-01-13 | 2018-08-01 | 2019-01-14 | 2019-03-10 | 2019-07-05 | 2019-09-15 | 2020-01-06 | 2020-03-14 | 2020-03-16
7 | 14 | 3 bhk | 1940 | 2018-05-10 | 2018-09-06 | 2019-06-01 | 25.11.19 | 14.12.19 | 2020-01-26 | 2020-06-01 | 2020-06-27
8 | 15 | 3 bhk | 1940 | 2018-03-05 | 2018-09-06 | 2019-06-01 | 10.11.19 | 14.12.19 | 2020-02-26 | 2020-06-22
9 | 16 | 3 bhk | 1940 | 2018-01-07 | 2018-07-07 | 2018-12-12 | 2019-05-14 | 2019-07-07 | 2019-09-15 | 01.12.19 | 2020-01-06 | 2020-02-20
10 | 33 | 3 bhk | 1940 | 2018-10-25 | 2018-02-10 | 2018-12-05 | 2019-04-03 | 2019-05-15 | 2019-08-07 | 2019-09-15 | 2020-03-20 | 2020-05-25
11 | 34 | 3 bhk | 1940 | 2018-12-18 | 2018-02-13 | 2018-11-08 | 2019-02-27 | 2019-04-03 | 2019-05-18 | 2019-09-15 | 2019-10-04 | 2019-10-05
12 | 35 | 3 bhk | 1940 | 2017-11-20 | 2018-02-13 | 2018-10-15 | 2019-02-15 | 2019-04-03 | 2019-05-19 | 2019-09-20 | 2020-05-15
13 | 36 | 3 bhk | 1940 | 2017-11-20 | 2018-02-21 | 2018-06-22 | 2019-02-04 | 2019-04-03 | 2019-05-20 | 2019-10-01 | 2020-06-27
14 | 37 | 3 bhk | 1820 | 2018-07-18 | 2018-12-10 | 2019-09-10 | 2020-05-25 | 2020-06-09
15 | 42 | 3 bhk | 1940 | 2018-02-26 | 2018-09-27 | 2019-08-10 | 26.10.19 | 01.12.19 | 2020-03-04 | 2020-06-22
16 | 43 | 3 bhk | 1940 | 2018-05-01 | 2018-09-25 | 2019-04-17 | 25.11.19 | 01.12.19 | 2020-03-06 | 2020-06-22
17 | 44 | 3 bhk | 1940 | 2018-01-08 | 2018-09-17 | 2019-03-11 | 2019-08-18 | 2019-09-25 | 06.01.2020 | 2020-03-01 | 2020-03-14 | 2020-03-16
18 | 48 | 3 bhk | 1940 | 2017-12-14 | 2018-03-08 | 2018-11-24 | 2018-05-15 | 2019-09-01 | 18.10.19 | 2020-01-27
19 | 55 | 3 bhk | 1940 | 2017-09-21 | 2018-01-02 | 2018-10-15 | 2019-04-03 | 2019-07-01 | 2019-09-15 | 26.10.19
20 | 56 | 3 bhk | 1940 | 2017-08-04 | 2018-01-02 | 2018-07-19 | 2019-02-05 | 2019-03-05 | 2019-04-05 | 2019-08-05 | 2019-09-15 | 2019-09-01
21 | 63 | 3 bhk | 1940 | 2017-10-25 | 2017-12-27 | 2018-08-28 | 2019-02-04 | 2019-06-01 | 2019-07-01 | 2019-09-15 | 01.12.19 | 2019-12-10
22 | 64 | 3 bhk | 1940 | 2018-07-04 | 2019-03-07 | 2019-03-15 | 2019-02-04 | 01.12.19
23 | 65 | 3 bhk | 1940 | 2017-09-25 | 2017-01-10 | 2018-10-01 | 2019-02-04 | 2019-06-01 | 2019-07-01 | 2019-09-25 | 01.12.19 | 2019-12-10
24 | 69 | 3 bhk | 1940 | 2017-09-24 | 2018-02-24 | 2018-09-12 | 2018-09-12 | 2018-12-12 | 2018-12-20 | 2018-12-28 | 2019-03-01 | 2019-04-10
25 | 75 | 3 bhk | 1940 | 24.02.18 | 2019-08-05 | 2019-02-26 | 2019-07-01 | 2019-07-07 | 2019-08-07 | 2019-09-20 | 26.10.19 | 2019-11-10
26 | 76 | 3 bhk | 1940 | 2018-02-21 | 2018-08-30 | 2019-04-03 | 2019-10-01 | 25.10.19 | 2020-03-01 | 2020-07-05
27 | 78 | 3 bhk | 1940 | 2017-08-21 | 2017-10-30 | 2018-02-01 | 2018-05-01 | 2018-06-10 | 2018-08-10 | 2018-10-10 | 2019-02-26 | 2019-05-01
28 | 82 | 3 bhk | 1940 | 2017-09-25 | 2017-12-23 | 2018-07-10 | 2018-12-20 | 2019-02-04 | 2019-04-10 | 2019-05-21 | 2019-10-04 | 2019-12-05
29 | 83 | 3 bhk | 1940 | 2018-08-01 | 2018-12-16 | 2018-10-21 | 2019-04-10 | 2019-05-02 | 2019-08-02 | 2019-10-04 | 2019-12-01 | 2019-12-10
30 | 84 | 3 bhk | 1940 | 2018-01-08 | 2018-04-04 | 2018-10-29 | 2019-03-25 | 2019-03-30 | 2019-04-03 | 2019-05-20 | 2019-06-08 | 2019-06-18
31 | 85 | 3 bhk | 1940 | 2017-08-21 | 2017-11-01 | 2018-02-06 | 2018-11-01 | 2018-11-14 | 2018-03-20 | 2019-05-19 | 2019-06-01 | 2019-06-10
32 | 90 | 3 bhk | 1940 | 2017-11-21 | 2018-02-16 | 2018-07-18 | 2019-01-03 | 2019-01-18 | 2019-06-06 | 2020-06-22
33 | 91 | 3 bhk | 1940 | 2017-11-21 | 2019-02-14 | 2018-06-12 | 2018-11-01 | 2019-01-05 | 2019-02-23 | 2019-06-01 | 2019-09-15 | 2019-10-01
34 | 96 | 3 bhk | 1820 | 2018-06-18 | 2018-08-30 | 2019-03-15 | 2019-08-15 | 26.10.19 | 2020-03-20
35 | 97 | 3 bhk | 1820 | 2017-12-07 | 2018-05-15 | 2019-02-17 | 2019-07-07 | 2019-07-15 | 2019-12-20 | 2020-01-06 | 2020-05-25 | 2020-06-09
36 | 100 | 3 bhk | 1820 | 2018-06-18 | 2018-07-12 | 2019-03-23 | 2019-08-19 | 2019-08-22 | 2020-12-28 | 2020-03-01 | 2020-06-15
37 | 101 | 3 bhk | 1820 | 2018-06-18 | 2018-07-18 | 2019-03-23 | 2020-05-20 | 2020-05-25
38 | 102 | 3 bhk | 1820 | 2018-06-26 | 2019-02-15 | 2019-08-21 | 2020-03-01 | 2020-07-05
39 | 103 | 3 bhk | 1820 | 2019-06-26 | 2019-02-05 | 2019-09-20
40 | 104 | 3 bhk | 1940 | 2017-08-04 | 2017-11-01 | 2018-06-24 | 2018-11-10 | 2018-12-10 | 2019-06-06 | 01.12.19 | 2020-03-16
41 | 107 | 3 bhk | 1820 | 2018-08-01 | 2018-12-01 | 2019-09-15 | 18.11.19 | 2019-12-20 | 2020-01-01 | 2020-03-01 | 2020-03-14 | 2020-05-25
42 | 108 | 3 bhk | 1820 | 2018-02-08 | 2018-10-15 | 2019-05-06 | 26.10.19 | 2019-12-20 | 2020-01-05 | 2020-01-27 | 2020-03-06 | 2020-03-14
43 | 112 | 3 bhk | 1940 | 2017-08-15 | 2018-02-24 | 2018-06-21 | 2018-11-14 | 2019-01-25 | 2019-02-04 | 2019-02-26 | 2019-05-01 | 2019-06-01
44 | 113 | 3 bhk | 1820 | 2018-06-12 | 2018-07-26 | 2018-12-27 | 2019-06-24 | 2019-10-04 | 18.10.19 | 2019-12-20 | 2020-03-01 | 2020-03-16
45 | 114 | 3 bhk | 1820 | 2018-05-02 | 2018-07-04 | 2018-12-27 | 2019-04-25 | 2019-07-18
46 | 115 | 3 bhk | 1820 | 2018-05-03 | 2018-07-04 | 2018-12-27 | 2019-04-04 | 2019-07-08
47 | 116 | 3 bhk | 1820 | 2018-06-10 | 2018-07-23 | 2018-11-06 | 2019-02-23 | 2019-06-25 | 2019-09-15 | 2020-01-27
48 | 117 | 3 bhk | 1820 | 2018-05-02 | 2018-07-23 | 2018-11-06 | 2019-01-24 | 2019-06-26 | 2019-09-15 | 2019-12-01
49 | 119 | 3 bhk | 1820 | 2018-11-01 | 2018-12-01 | 2019-12-30 | 2019-03-23 | 2019-07-01 | 18.10.19 | 2019-12-14
50 | 120 | 3 bhk | 1820 | 2018-05-10 | 2018-07-31 | 2019-01-30 | 2019-12-14 | 2019-10-01 | 2020-02-25
51 | 121 | 3 bhk | 1820 | 2018-05-10 | 2018-08-25 | 2019-02-04 | 2019-12-14 | 2020-01-01 | 2020-02-10
52 | 122 | 3 bhk | 1820 | 2018-02-08 | 2018-08-25 | 2019-03-07 | 2019-12-14 | 2020-01-01 | 2020-02-26
53 | 123 | 3 bhk | 1820 | 2018-02-08 | 2018-08-23 | 2019-05-10 | 2019-10-26 | 2020-01-01 | 2020-02-26
54 | 124 | 3 bhk | 1820 | 2017-11-20 | 2018-08-09 | 2019-04-03 | 2019-07-01 | 2020-01-01 | 2020-02-28
55 | 125 | 3 bhk | 1820 | 2018-05-15 | 2018-10-16 | 2019-04-01 | 2019-11-25 | 2020-01-27 | 2020-02-10 | 2020-03-06
56 | 127 | 3 bhk | 1940 | 2018-06-06 | 2019-06-06 | 15.11.19 | 2020-03-20
57 | 128 | 3 bhk | 1820 | 2018-06-09 | 2019-06-17 | 26.10.19 | 2020-04-06
58 | 129 | 3 bhk | 1820 | 2018-08-14 | 2018-12-10 | 2019-08-14 | 2019-09-17 | 2019-09-30 | 2019-10-30 | 2019-12-30 | 2020-02-20 | 2020-02-27
59 | 130 | 3 bhk | 1820 | 2018-08-14 | 2018-12-10 | 2019-08-14 | 2019-12-26 | 2020-03-07
60 | 131 | 3 bhk | 1820 | 2018-06-04 | 2018-12-30 | 04.10.19
61 | 132 | 3 bhk | 1820 | 2018-06-04 | 2018-10-02 | 2019-11-11 | 2020-06-01
62 | 135 | 3 bhk | 1820 | 2017-12-24 | 2018-07-21 | 2019-05-14 | 2020-03-07 | 2020-06-01
63 | 136 | 3 bhk | 1820 | 2018-07-21 | 2019-03-01 | 2019-07-25 | 2019-12-01 | 10.12.19 | 2019-12-14 | 2020-01-06 | 2020-03-07 | 2020-03-16
64 | 137 | 3 bhk | 1820 | 2019-07-21 | 2018-12-24 | 2019-08-04 | 2020-03-20
65 | 182 | 3 bhk | 1585 | 2017-11-06 | 2017-12-28 | 2018-03-09 | 2018-09-20 | 2018-10-10 | 2018-10-20 | 2019-11-15 | 2019-12-20 | 2019-12-30
66 | 184 | 3 bhk | 1585 | 2018-10-10 | 2018-12-10 | 2019-03-07 | 2019-06-05 | 2019-10-01 | 2019-11-20 | 2019-12-14 | 2020-07-05
67 | 186 | 3 bhk | 1940 | 2018-02-04 | 2018-09-12 | 2019-05-01 | 2019-07-01 | 2019-07-07 | 2019-11-20 | 2019-12-01 | 2020-01-25 | 2020-02-25
68 | 187 | 3 bhk | 1585 | 2018-05-05 | 2018-07-07 | 2018-11-13 | 2019-02-23 | 2019-05-02 | 2019-05-21 | 2019-07-15 | 15-10-1- | 2019-12-01
69 | 188 | 3 bhk | 1585 | 2018-05-05 | 2018-07-07 | 2018-11-13 | 2019-02-13 | 2019-05-02 | 2019-05-14 | 2019-07-15 | 2019-09-06 | 2019-10-05
70 | 189 | 3 bhk | 1585 | 2018-06-04 | 2018-07-07 | 2018-11-13 | 2019-03-06 | 2019-05-02 | 2019-06-16 | 2019-07-15 | 2019-09-07 | 2019-10-05
71 | 190 | 3 bhk | 1585 | 2018-06-04 | 2018-07-07 | 2018-11-13 | 2019-03-29 | 2019-05-04 | 2019-06-01 | 2019-07-15 | 2019-09-07 | 2019-06-29
72 | 191 | 3 bhk | 1585 | 2018-05-08 | 2018-07-08 | 2018-11-14 | 2019-04-21 | 2019-05-04 | 2019-06-18 | 2019-07-15 | 2019-09-09 | 2019-10-05
73 | 194 | 3 bhk | 1585 | 2017-06-11 | 2018-07-09 | 2018-11-15 | 2019-04-22 | 2019-05-05 | 2019-06-19 | 2019-01-15 | 2019-09-10 | 2019-07-01
74 | 196 | 3 bhk | 1585 | 2018-12-10 | 2018-07-10 | 2018-11-16 | 2020-03-20
75 | 200 | 3 bhk | 1820 | 2017-08-12 | 2017-12-27 | 2018-07-17 | 2018-09-01 | 2018-09-10 | 2018-09-18 | 2019-02-20 | 2019-02-28 | 2019-08-01
76 | 201 | 3 bhk | 1820 | 2018-05-02 | 2018-05-22 | 2018-12-28 | 2018-06-23 | 2019-07-07 | 2019-08-25 | 2019-11-01 | 2019-11-06 | 2019-11-09
77 | 202 | 3 bhk | 1820 | 2018-05-03 | 2018-05-23 | 2018-12-28 | 2019-06-23 | 2019-07-07 | 2019-08-25 | 01-+11-19 | 2019-11-06 | 2019-11-09
78 | 203 | 3 bhk | 1820 | 2018-08-01 | 2018-11-26 | 2019-04-10 | 2019-08-01 | 2019-08-12 | 2019-12-14 | 2020-01-06
79 | 204 | 3 bhk | 1820 | 2018-08-01 | 2018-11-29 | 2019-03-21 | 2019-08-01 | 2019-08-12 | 2019-12-14 | 2020-03-01 | 2020-05-25
80 | 208 | 3 bhk | 1820 | 2017-11-03 | 2018-02-22 | 2018-06-19 | 2018-11-01 | 2019-02-28 | 2019-05-20 | 2019-06-24 | 2019-07-01 | 2019-10-30
81 | 209 | 3 bhk | 1820 | 2018-01-06 | 2018-03-25 | 2018-11-10 | 2018-06-30 | 2018-07-07 | 2019-08-07 | 2019-09-28 | 2019-10-20 | 2019-12-01
82 | 210 | 3 bhk | 1820 | 2018-01-06 | 2018-03-14 | 2018-12-01 | 2019-06-30 | 2019-09-30 | 2020-01-30 | 2020-06-27
83 | 211 | 3 bhk | 1820 | 2017-12-07 | 2018-06-13 | 2019-01-25 | 2019-03-25 | 2019-09-20 | 2020-01-30 | 2020-06-22
84 | 212 | 3 bhk | 1820 | 2018-02-20 | 2018-06-13 | 2019-02-07 | 2019-03-25 | 2019-09-15 | 2020-02-20 | 2020-06-22
85 | 213 | 3 bhk | 1820 | 2017-09-21 | 2017-12-27 | 2018-05-13 | 2018-10-24 | 2018-12-14 | 2019-04-03 | 2019-06-05 | 2019-07-10 | 2019-07-15
86 | 217 | 3 bhk | 1820 | 2018-10-20 | 2019-01-25 | 2019-02-25 | 25.11.19 | 2019-12-01 | 2019-04-04
87 | 218 | 3 bhk | 1820 | 2018-02-20 | 2019-01-25 | 2019-02-25 | 25.11.19 | 2019-12-01 | 2020-05-18
88 | 219 | 3 bhk | 1820 | 2018-02-21 | 2018-09-03 | 2019-07-15 | 25.11.19 | 2019-12-01 | 2020-04-01
89 | 220 | 3 bhk | 1820 | 2019-01-08 | 2019-01-24 | 2019-07-31 | 2020-02-20 | 2020-03-07 | 2020-05-25
90 | 221 | 3 bhk | 1820 | 2019-01-08 | 2019-01-24 | 2019-06-30 | 2020-02-25 | 2020-03-07
91 | 224 | 3 bhk | 1820 | 2018-08-01 | 2018-10-10 | 2019-01-17 | 2019-04-18 | 2019-09-01 | 25.11.19 | 2019-12-25 | 2020-01-25
92 | 225 | 3 bhk | 1820 | 2018-01-08 | 2018-03-25 | 2018-12-25 | 2018-06-29 | 2018-10-29 | 2019-09-01 | 2019-10-04 | 2019-11-30 | 2020-02-25
93 | 226 | 3 bhk | 1820 | 2018-01-08 | 2018-04-04 | 2018-12-28 | 2019-06-29 | 2019-09-29 | 2019-12-14 | 2020-02-01 | 2020-05-20 | 2020-05-25
94 | 228 | 3 bhk | 1820 | 2017-11-06 | 2018-02-28 | 2018-03-09 | 2018-09-20 | 2018-10-10 | 2018-10-20 | 2019-01-15 | 2019-05-01 | 2019-06-01
95 | 239 | 3 bhk | 1940 | 2017-09-12 | 2017-12-30 | 2018-03-28 | 2018-05-28 | 2018-07-08 | 2018-08-28 | 2018-10-15 | 2019-02-18 | 2019-04-05
96 | 240 | 3 bhk | 1940 | 2018-07-05 | 2018-11-10 | 2018-12-23 | 2019-01-15 | 2019-09-15 | 2020-06-22
97 | 241 | 3 bhk | 1940 | 2017-09-12 | 2017-10-13 | 2018-07-19 | 2018-10-24 | 2018-12-14 | 2019-01-01 | 2019-05-01 | 2019-11-10 | 2019-12-01
98 | 242 | 3 bhk | 1940 | 2017-10-20 | 2017-12-27 | 2018-07-27 | 2018-10-25 | 2018-12-14 | 2019-02-25 | 2019-05-01 | 2019-12-10 | 2019-12-01
99 | 243 | 3 bhk | 1940 | 2017-11-21 | 2018-01-02 | 2018-09-06 | 2018-10-29 | 2018-12-19 | 2019-02-28 | 2019-05-10 | 2020-07-03
100 | 252 | 3 bhk | 1940 | 2017-11-05 | 2018-01-06 | 14-011-18 | 2019-04-03 | 2019-05-01 | 2019-07-07 | 2019-10-01 | 2019-12-10
101 | 254 | 3 bhk | 1820 | 2018-05-07 | 2018-08-16 | 2018-08-20 | 2020-03-20 | 2020-07-05
102 | 256 | 3 bhk | 1820 | 2018-10-05 | 2019-02-21 | 26.10.19 | 2020-02-25
103 | 257 | 3 bhk | 1820 | 2018-06-06 | 2019-09-18 | 2019-09-25 | 2020-07-05
104 | 258 | 3 bhk | 1820 | 2018-01-01 | 2018-10-16 | 2019-09-26 | 2020-04-05
105 | 282 | 3 bhk | 1820 | 2018-06-25 | 2018-12-25 | 2019-07-15 | 2020-04-08 | 2020-07-01
106 | 283 | 3 bhk | 1820 | 2018-06-25 | 2018-12-26 | 2019-07-06 | 2020-02-25 | 2020-03-16 | 2020-05-17 | 2020-06-22
107 | 284 | 3 bhk | 1820 | 2018-06-25 | 2018-10-29 | 2019-03-28 | 2020-03-07 | 2020-07-01
108 | 285 | 3 bhk | 1820 | 2018-05-04 | 2018-10-11 | 2019-01-31 | 2020-01-05 | 2020-01-15 | 2020-01-20 | 2020-02-25 | 2020-06-22
109 | 286 | 3 bhk | 1820 | 2018-05-08 | 2018-08-01 | 2018-11-01 | 2020-03-07 | 2020-06-15 | 2020-07-06
110 | 287 | 3 bhk | 1820 | 2018-05-06 | 2018-07-26 | 2019-01-03 | 2019-10-25 | 2020-05-01 | 2020-06-20
111 | 294 | 3 bhk | 1820 | 2018-05-25 | 2018-07-07 | 2018-10-25 | 2020-07-06
112 | 295 | 3 bhk | 1820 | 2017-09-20 | 2017-12-16 | 2018-08-05 | 2018-11-20 | 2018-12-13 | 2019-04-03 | 2019-05-20 | 2019-09-20 | 2019-11-08