## Anx - A - Attendance details
Annexure - A - Send Weekly
Details of labour charges
Name of contractor: |  | B. Anand
Company name: |  | Homeline Infra
Project name: |  | VOCLLP
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Work Type | Worker Type | Quantity | Rate | Amount
1 | Civil work | Mason | 0 | 575 | 0
2 | Civil work | Male helper | 0 | 400 | 0
3 | Civil work | Female helper | 0 | 350 | 0
4 | RCC work | Mason | 0 | 550 | 0
5 | RCC work | Male helper |  | 400 | 0
6 | RCC work | Female helper |  |  | 0
7 | Earth work | Mason |  |  | 0
8 | Earth work | Male helper |  |  | 0
9 | Earth work | Female helper |  |  | 0
10 | Electrician | Mason |  |  | 0
11 | Electrician | Male helper |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
| Total |  |  |  | 0
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - B - Hire charges
Annexure - B - Send Weekly
Details of hire charges
Name of contractor: |  | B. Anand
Company name: |  | Homeline Infra
Project name: |  | VOCLLP
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Equipment Type | Quantity | Rate | Units | Amount
1 | jcb |  | 900 | nos | 0
2 | tractor |  | 1800 | nos | 0
3 |  |  |  | nos | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
| Total |  |  |  | 0
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - C - Material received
Annexure - C - send weekly
Details of magterial received
Name of contractor: |  | B. Anand
Company name: |  | Homeline Infra
Project name: |  | VOCLLP
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Material type | Received date | Inward no. | Quantity | Units | Rate | Amount
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15
16
17
18
19
20
21
22
23
24 | [6 empty] | 0
| Total | [5 empty] | 0
Payment approved by MD:
Prepared by: |  |  |  | Approved by: |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - D - Milestone report
Annexure - D - send weekly
Mile stone report for CR-
Company name: |  |  |  | Villa Orchids
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 2020-04-30
Note: | Prepare the statement for all the villas in the project.
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Completion of plinth | Completion of RCC | Completion of brickwork and plastering | Completion of stage I | Completion of stage II | Completion of stage III | Completion of stage IV | Date of physical posession
1 | 8 | 3BHK | 1940 | 2018-01-16
2 | 9 | 3BHK | 1940 | 2018-04-30
3 | 10 | 3BHK | 1940 | 2018-05-04
4 | 11 | 3BHK | 1940 | 2019-01-09
5 | 12 | 3BHK | 1940 | 2018-01-09
6 | 13 | 3BHK | 1940 | 2018-01-13
7 | 14 | 3BHK | 1940 | 2018-05-10
8 | 15 | 3BHK | 1940 | 2018-03-05
9 | 16 | 3BHK | 1940 | 2018-01-07
10 | 33 | 3BHK | 1940 | 2017-10-25
11 | 34 | 3BHK | 1940 | 2017-12-18
12 | 35 | 3BHK | 1940 | 2017-11-20
13 | 36 | 3BHK | 1940 | 2017-11-20
14 | 42 | 3BHK | 1940 | 2018-02-26
15 | 43 | 3BHK | 1940 | 2018-05-01
16 | 44 | 3BHK | 1940 | 2018-01-08
17 | 48 | 3BHK | 1940 | 2017-12-14
18 | 55 | 3BHK | 1940 | 2017-09-21
19 | 56 | 3BHK | 1940 | 2017-04-08
20 | 63 | 3BHK | 1940 | 2017-10-25
21 | 64 | 3BHK | 1940 | 2017-11-21
22 | 65 | 3BHK | 1940 | 2017-09-25
23 | 69 | 3BHK | 1940 | 2017-09-24
24 | 75 | 3BHK | 1940 | 2018-02-24
25 | 76 | 3BHK | 1940 | 2018-02-21
26 | 125 | 3BHK | 1820 | 2018-05-15
27 | 78 | 3BHK | 1940 | 2017-08-21
28 | 82 | 3BHK | 1940 | 2017-09-25
29 | 83 | 3BHK | 1940 | 2017-09-25
30 | 84 | 3BHK | 1940 | 2018-01-08
31 | 85 | 3BHK | 1940 | 2017-08-21
32 | 97 | 3BHK | 1820 | 2017-07-12
33 | 104 | 3BHK | 1940 | 2017-04-08
34 | 108 | 3BHK | 1820 | 2018-02-08
35 | 112 | 3BHK | 1940 | 2017-08-15
36 | 119 | 3BHK | 1585 | 2018-04-01
37 | 120 | 3BHK | 1820 | 2018-05-10
38 | 121 | 3BHK | 1820 | 2018-05-10
39 | 122 | 3BHK | 1820 | 2018-02-08
40 | 123 | 3BHK | 1820 | 2018-02-08
41 | 124 | 3BHK | 1820 | 2017-11-20
42 | 225 | 3BHK | 1820 | 2018-01-08
43 | 226 | 3BHK | 1820 | 2018-01-08
44 | 224 | 3BHK | 1820 | 2018-01-08
45
46 | 135 | 3BHK | 1820 | 2018-02-04
47 | 136 | 3BHK | 1820 | 2018-02-05
48 | 137 | 3BHK | 1820 | 2018-02-22
49 | 184 | 3BHK | 1585 | 2018-01-06
50 | 219 | 3BHK | 1820 | 2018-02-21
51 | 218 | 3BHK | 1820 | 2018-02-21
52 | 220 | 3BHK | 1820 | 2018-02-21
53 | 221 | 3BHK | 1820 | 2018-01-08
54 | 186 | 3BHK | 1940 | 2018-02-04
55 | 212 | 3BHK | 1820 | 2018-02-22
56 | 211 | 3BHK | 1820 | 2017-12-07
57 | 217 | 3BHK | 1820 | 2018-01-08
58 | 209 | 3BHK | 1820 | 2018-01-06
59 | 210 | 3BHK | 1820 | 2018-01-06
60 | 242 | 3BHK | 1940 | 2017-10-20
61 | 252 | 3BHK | 1940 | 2017-05-11
62 | 243 | 3BHK | 1940 | 2017-11-21
63 | 240 | 3BHK | 1940 | 2017-11-19
64 | 200 | 3BHK | 1820 | 2017-08-12
65 | 239 | 3BHK | 1940 | 2017-09-12
66 | 241 | 3BHK | 1940 | 2017-08-12
67 | 213 | 3BHK | 1820 | 2017-09-21
68 | 295 | 3BHK | 1820 | 2017-09-20
69 | 196 | 3BHK | 1740 | 18.04.17

## Anx - E1 -Estimate of work done
Annexure - E1 - Details of partial work done and not yet billed - send on the last Saturday of the month-
Name of contractor: |  |  |  | B- Anand
Company name: |  |  |  | Homeline Infra
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 2020-05-29
Note: | Enter value beween 1&100 as approximate pecentage of work completed- Enter 0 where work is completed and billed.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | Construction contract value | Value of work done
1 | 8 | 3BHK | 1940 | 2018-01-16 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
2 | 9 | 3BHK | 1940 | 2018-04-30 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
3 | 10 | 3BHK | 1940 | 2018-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
4 | 11 | 3BHK | 1940 | 2019-01-09 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
5 | 12 | 3BHK | 1940 | 2018-01-09 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
6 | 13 | 3BHK | 1940 | 2018-01-13 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
7 | 14 | 3BHK | 1940 | 2018-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
8 | 15 | 3BHK | 1940 | 2018-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
9 | 16 | 3BHK | 1940 | 2018-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
10 | 33 | 3BHK | 1940 | 2017-10-25 | 0 | 0 | 0 | 0 | 100 | 10 | 650 | 1261000 | 126100
11 | 34 | 3BHK | 1940 | 2017-12-18 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
12 | 35 | 3BHK | 1940 | 2017-11-20 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
13 | 36 | 3BHK | 1940 | 2017-11-20 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
14 | 42 | 3BHK | 1940 | 2018-02-26 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
15 | 43 | 3BHK | 1940 | 2018-05-01 | 0 | 0 | 0 | 0 |  |  | 650 | 1261000 | 0
16 | 44 | 3BHK | 1940 | 2018-01-08 | 0 | 0 | 0 | 0 |  |  | 650 | 1261000 | 0
17 | 48 | 3BHK | 1940 | 2017-12-14 | 0 | 0 | 0 | 0 |  |  | 650 | 1261000 | 113490
18 | 55 | 3BHK | 1940 | 2017-09-21 | 0 | 0 | 0 | 0 |  |  | 650 | 1261000 | 0
19 | 56 | 3BHK | 1940 | 2017-04-08 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
20 | 63 | 3BHK | 1940 | 2017-10-25 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
21 | 64 | 3BHK | 1940 | 2017-11-21 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
22 | 65 | 3BHK | 1940 | 2017-09-25 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
23 | 69 | 3BHK | 1940 | 2017-09-24 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
24 | 75 | 3BHK | 1940 | 2018-02-24 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
25 | 76 | 3BHK | 1940 | 2018-02-21 | 0 | 0 |  |  |  | 0 | 650 | 1261000 | 0
26 | 125 | 3BHK | 1820 | 2018-05-15 | 0 | 0 |  |  |  | 0 | 650 | 1183000 | 0
27 | 78 | 3BHK | 1940 | 2017-08-21 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
28 | 82 | 3BHK | 1940 | 2017-09-25 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
29 | 83 | 3BHK | 1940 | 2017-09-25 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
30 | 84 | 3BHK | 1940 | 2018-01-08 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
31 | 85 | 3BHK | 1940 | 2017-08-21 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1261000 | 0
32 | 97 | 3BHK | 1820 | 2017-07-12 | 0 | 0 | 0 | 0 | 100 | 10 | 650 | 1183000 | 118300
33 | 104 | 3BHK | 1940 | 2017-04-08 | 0 | 0 | 0 | 0 | 100 | 10 | 650 | 1261000 | 126100
34 | 108 | 3BHK | 1820 | 2018-02-08 | 0 | 0 | 0 | 100 |  | 20 | 650 | 1183000 | 236600
35 | 112 | 3BHK | 1940 | 2017-08-15 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
36 | 119 | 3BHK | 1585 | 2018-04-01 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1030250 | 0
37 | 120 | 3BHK | 1820 | 2018-05-10 | 0 | 0 | 0 |  |  | 0 | 650 | 1183000 | 0
38 | 121 | 3BHK | 1820 | 2018-05-10 | 0 | 0 |  |  |  | 0 | 650 | 1183000 | 0
39 | 122 | 3BHK | 1820 | 2018-02-08 | 0 | 0 |  |  |  | 0 | 650 | 1183000 | 0
40 | 123 | 3BHK | 1820 | 2018-02-08 | 0 | 0 |  |  |  | 0 | 650 | 1183000 | 0
41 | 124 | 3BHK | 1820 | 2017-11-20 | 0 |  |  |  |  | 0 | 650 | 1183000 | 0
42 | 225 | 3BHK | 1820 | 2018-01-08 | 0 | 0 | 0 | 0 | 100 | 10 | 650 | 1183000 | 118300
43 | 226 | 3BHK | 1820 | 2018-01-08 | 0 | 0 | 100 | 100 | 100 | 55 | 650 | 1183000 | 650650
44 | 224 | 3BHK | 1820 | 2018-01-08 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1183000 | 0
45 | 125 | 3BHK | 1820 | 2018-05-15 | 0 |  |  |  |  | 0 | 650 | 1183000 | 0
46 | 135 | 3BHK | 1820 | 2018-02-04 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1183000 | 0
47 | 136 | 3BHK | 1820 | 2018-02-05 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1183000 | 0
48 | 137 | 3BHK | 1820 | 2018-02-22 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1183000 | 0
49 | 184 | 3BHK | 1585 | 2018-01-06 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1030250 | 0
50 | 219 | 3BHK | 1820 | 2018-02-21 | 0 | 0 | 100 | 100 |  | 45 | 650 | 1183000 | 532350
51 | 218 | 3BHK | 1820 | 2018-02-21 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1183000 | 0
52 | 220 | 3BHK | 1820 | 2018-02-21 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1183000 | 0
53 | 221 | 3BHK | 1820 | 2018-01-08 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1183000 | 0
54 | 186 | 3BHK | 1940 | 2018-02-04 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
55 | 212 | 3BHK | 1820 | 2018-02-22 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1183000 | 0
56 | 211 | 3BHK | 1820 | 2017-12-07 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1183000 | 0
57 | 217 | 3BHK | 1820 | 2018-01-08 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1183000 | 0
58 | 209 | 3BHK | 1820 | 2018-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1183000 | 0
59 | 210 | 3BHK | 1820 | 2018-01-06 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1183000 | 0
60 | 242 | 3BHK | 1940 | 2017-10-20 | 0 | 0 | 0 | 0 | 100 | 10 | 650 | 1261000 | 126100
61 | 252 | 3BHK | 1940 | 2017-05-11 | 0 | 0 | 0 | 0 | 100 | 10 | 650 | 1261000 | 126100
62 | 243 | 3BHK | 1940 | 2017-11-21 | 0 | 0 | 0 | 0 | 100 | 10 | 650 | 1261000 | 126100
63 | 240 | 3BHK | 1940 | 2017-11-19 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
64 | 200 | 3BHK | 1820 | 2017-08-12 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1183000 | 0
65 | 239 | 3BHK | 1940 | 2017-09-12 | 0 | 0 | 0 | 0 |  | 0 | 650 | 1261000 | 0
66 | 241 | 3BHK | 1940 | 2017-08-12 | 0 | 0 | 0 | 0 | 100 | 10 | 650 | 1261000 | 126100
67 | 213 | 3BHK | 1820 | 2017-09-21 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1183000 | 0
68 | 295 | 3BHK | 1820 | 2017-09-20 | 0 | 0 | 0 | 0 | 100 | 10 | 650 | 1183000 | 118300
69 | 196 | 3BHK | 1820 | 2018-04-18 | 0 | 100 | 0 | 0 | 0 |  | 650 | 1183000 | 0
70 | 258 | 3BHK | 1820 | 2019-04-19 | [5 empty] | 0 |  | 0 | 0
75 | [9 empty] | 0 |  | 0 | 0
76 | [9 empty] | 0 |  | 0 | 0
77 | [9 empty] | 0 |  | 0 | 0
|  | Total | 131610 |  | 0 | 1.4925 | 3.2258 | 4.918 | 32.2581 | 3.0882 | 650 | 84363500 | 2644590

## Anx - E2 - work done & billed
Annexure - E2 - work completed and bill raised -send on the last Saturday of the month. | [14 empty] | 0
Name of contractor: |  |  |  | B. Anand
Company name: |  |  |  | Homeline Infra
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 2020-05-29
Note: | Enter vlaue 1 if work is completed and billed. Enter 0 otherwise. This statement must match billing database.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100 |  |  | 0
S No | Villa no. | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | GST | Construction contract value | Value of work done | Advance Paid | Advance adjusted
1 | 8 | 3BHK | 1940 | 2018-01-16 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
2 | 9 | 3BHK | 1940 | 2018-04-30 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
3 | 10 | 3BHK | 1940 | 2018-05-04 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1487980 | 297596 |  | 0
4 | 11 | 3BHK | 1940 | 2019-01-09 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
5 | 12 | 3BHK | 1940 | 2018-01-09 | 1 | 1 | 0 | 0 | 0 | 45 | 650 | 18 | 1487980 | 669591 |  | 0
6 | 13 | 3BHK | 1940 | 2018-01-13 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
7 | 14 | 3BHK | 1940 | 2018-05-10 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
8 | 15 | 3BHK | 1940 | 2018-03-05 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
9 | 16 | 3BHK | 1940 | 2018-01-07 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
10 | 33 | 3BHK | 1940 | 2017-10-25 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1487980 | 1487980 |  | 0
11 | 34 | 3BHK | 1940 | 2017-12-18 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1487980 | 1487980 |  | 0
12 | 35 | 3BHK | 1940 | 2017-11-20 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
13 | 36 | 3BHK | 1940 | 2017-11-20 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
14 | 42 | 3BHK | 1940 | 2018-02-26 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
15 | 43 | 3BHK | 1940 | 2018-05-01 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
16 | 44 | 3BHK | 1940 | 2018-01-08 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
17 | 48 | 3BHK | 1940 | 2017-12-14 | 1 | 1 | 1 | 0 | 0 | 70 | 650 | 18 | 1487980 | 1041586 |  | 0
18 | 55 | 3BHK | 1940 | 2017-09-21 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
19 | 56 | 3BHK | 1940 | 2017-04-08 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1487980 | 1487980 |  | 0
20 | 63 | 3BHK | 1940 | 2017-10-25 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1487980 | 1487980 |  | 0
21 | 64 | 3BHK | 1940 | 2017-11-21 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1487980 | 297596 |  | 0
22 | 65 | 3BHK | 1940 | 2017-09-25 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
23 | 69 | 3BHK | 1940 | 2017-09-24 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1487980 | 1487980 |  | 0
24 | 75 | 3BHK | 1940 | 2018-02-24 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
25 | 76 | 3BHK | 1940 | 2018-02-21 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
26 | 125 | 3BHK | 1820 | 2018-05-15 | 1 | 1 | 1 | 0 | 0 | 70 | 650 | 18 | 1395940 | 977158 |  | 0
27 | 78 | 3BHK | 1940 | 2017-08-21 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1487980 | 1487980 |  | 0
28 | 82 | 3BHK | 1940 | 2017-09-25 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
29 | 83 | 3BHK | 1940 | 2017-09-25 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1487980 | 297596 |  | 0
30 | 84 | 3BHK | 1940 | 2018-01-08 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1487980 | 1487980 |  | 0
31 | 85 | 3BHK | 1940 | 2017-08-21 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
32 | 97 | 3BHK | 1820 | 2017-07-12 | 1 | 1 | 1 | 0 | 0 | 70 | 650 | 18 | 1395940 | 977158 |  | 0
33 | 104 | 3BHK | 1940 | 2017-04-08 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
34 | 108 | 3BHK | 1820 | 2018-02-08 | 1 | 1 | 1 | 0 | 0 | 70 | 650 | 18 | 1395940 | 977158 |  | 0
35 | 112 | 3BHK | 1940 | 2017-08-15 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1487980 | 1487980 |  | 0
36 | 119 | 3BHK | 1585 | 2018-04-01 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1215695 | 243139 |  | 0
37 | 120 | 3BHK | 1820 | 2018-05-10 | 1 | 1 | 0 | 0 | 0 | 45 | 650 | 18 | 1395940 | 628173 |  | 0
38 | 121 | 3BHK | 1820 | 2018-05-10 | 1 | 1 | 0 | 0 | 0 | 45 | 650 | 18 | 1395940 | 628173 |  | 0
39 | 122 | 3BHK | 1820 | 2018-02-08 | 1 | 1 | 0 | 0 | 0 | 45 | 650 | 18 | 1395940 | 628173 |  | 0
40 | 123 | 3BHK | 1820 | 2018-02-08 | 1 | 1 | 0 | 0 | 0 | 45 | 650 | 18 | 1395940 | 628173 |  | 0
41 | 124 | 3BHK | 1820 | 2017-11-20 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1395940 | 279188 |  | 0
42 | 225 | 3BHK | 1820 | 2018-01-08 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1395940 | 1256346 |  | 0
43 | 226 | 3BHK | 1820 | 2018-01-08 | 1 | 1 |  |  | 0 | 45 | 650 | 18 | 1395940 | 628173 |  | 0
44 | 224 | 3BHK | 1820 | 2018-01-08 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1395940 | 279188 |  | 0
45 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 18 | 0 | 0 |  | 0
46 | 135 | 3BHK | 1820 | 2018-02-04 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1395940 | 279188 |  | 0
47 | 136 | 3BHK | 1820 | 2018-02-05 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1395940 | 279188 |  | 0
48 | 137 | 3BHK | 1820 | 2018-02-22 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1395940 | 279188 |  | 0
49 | 184 | 3BHK | 1585 | 2018-01-06 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1215695 | 243139 |  | 0
50 | 219 | 3BHK | 1820 | 2018-02-21 | 1 | 1 |  |  | 0 | 45 | 650 | 18 | 1395940 | 628173 |  | 0
51 | 218 | 3BHK | 1820 | 2018-02-21 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1395940 | 279188 |  | 0
52 | 220 | 3BHK | 1820 | 2018-02-21 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1395940 | 279188 |  | 0
53 | 221 | 3BHK | 1820 | 2018-01-08 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1395940 | 279188 |  | 0
54 | 186 | 3BHK | 1940 | 2018-02-04 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
55 | 212 | 3BHK | 1820 | 2018-02-22 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1395940 | 1256346 |  | 0
56 | 211 | 3BHK | 1820 | 2017-12-07 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1395940 | 1256346 |  | 0
57 | 217 | 3BHK | 1820 | 2018-01-08 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1395940 | 279188 |  | 0
58 | 209 | 3BHK | 1820 | 2018-01-06 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1395940 | 1395940 |  | 0
59 | 210 | 3BHK | 1820 | 2018-01-06 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1395940 | 1256346 |  | 0
60 | 242 | 3BHK | 1940 | 2017-10-20 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
61 | 252 | 3BHK | 1940 | 2017-05-11 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
62 | 243 | 3BHK | 1940 | 2017-11-21 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
63 | 240 | 3BHK | 1940 | 2017-11-19 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1487980 | 297596 |  | 0
64 | 200 | 3BHK | 1820 | 2017-08-12 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1395940 | 1395940 |  | 0
65 | 239 | 3BHK | 1940 | 2017-09-12 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1487980 | 1487980 |  | 0
66 | 241 | 3BHK | 1940 | 2017-08-12 | 1 | 1 | 1 | 1 |  | 90 | 650 | 18 | 1487980 | 1339182 |  | 0
67 | 213 | 3BHK | 1820 | 2017-09-21 | 1 | 1 | 1 | 1 | 1 | 100 | 650 | 18 | 1395940 | 1395940 |  | 0
68 | 295 | 3BHK | 1820 | 2017-09-20 | 1 | 1 | 1 | 1 | 0 | 90 | 650 | 18 | 1395940 | 1256346 |  | 0
69 | 196 | 3BHK | 1585 | 18.04.17 | 1 | 0 | 0 | 0 | 0 | 20 | 650 | 18 | 1215695 | 243139 |  | 0
70 | 258 | 3BHK | 1820 | 18.04.18 |  | 0 |  |  |  | 0 | 650 | 18 | 1395940 | 0 |  | 0
71 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
72 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
77 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
110 | [9 empty] | 0 | 0 |  | 0 | 0 |  | 0
|  | Total | 129555 |  | 68 | 52 | 45 | 41 | 12 | 63.8514 | 640.8451 | 18 | 99368685 | 68845920 | 0 | 0

## Anx - F -Summary of accounts
Annexure - F - Summary of accounts -send on the last Saturday of the month.
Name of contractor: |  | B. Anand
Company name: |  | Homeline Infra
Project name: |  | VOCLLP
Date: |  | 2020-05-29
S No | Summary - of credits | Amount
1 | Work completed & billed | 68845920
2 | Unbilled amount | 2644590
3 | Mobilization advance paid | 0
4 | Payment for increase in rate form ___ to ____
5 | Payment for increase in rate form ___ to ____
6 | Other credits
7 | Club house - billed value
8 | Club house - unbilled value - approx.
9
10
| Total A | 71490510
S No | Summary - of debits | Amount
1 | Mobilization advance adjusted | 0
2 | Amount paid | 62951987
3 | Other debits
4
5
6
7
8
9
10
| Total B | 62951987
| Net payable to contractor (A-B) | 8538523