## Anx - A - Attendance details
Annexure - A - Send Weekly
Details of labour charges
Name of contractor: |  | M Venakt raju
Company name: |  | MVR Constructions
Project name: |  | VOCLLP
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Work Type | Worker Type | Quantity | Rate | Amount
1 | Civil work | Mason | 15 | 575 | 8625
2 | Civil work | Male helper | 15 | 400 | 6000
3 | Civil work | Female helper |  | 350 | 0
4 | RCC work | Mason |  | 575 | 0
5 | RCC work | Male helper |  | 400 | 0
6 | RCC work | Female helper |  |  | 0
7 | Earth work | Mason |  |  | 0
8 | Earth work | Male helper |  | 450 | 0
9 | Earth work | Female helper |  | 400 | 0
10 | Electrician | Mason |  |  | 0
11 | Electrician | Male helper |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
| Total |  |  |  | 14625
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - B - Hire charges
Annexure - B - Send Weekly
Details of hire charges
Name of contractor: |  | M Venakt raju
Company name: |  | MVR Constructions
Project name: |  | VOCLLP
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Equipment Type | Quantity | Rate | Units | Amount
1 |  |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
| Total |  |  |  | 0
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - C - Material received
Annexure - C - send weekly
Details of magterial received
Name of contractor: |  | M Venakt raju
Company name: |  | MVR Constructions
Project name: |  | VOCLLP
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Material type | Received date | Inward no. | Quantity | Units | Rate | Amount
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15
16
17
18
19
20
21
22
23
24 | [6 empty] | 0
| Total | [5 empty] | 0
Payment approved by MD:
Prepared by: |  |  |  | Approved by: |  | MDs approval
Name | Asuresh
Date | 2020-07-24

## Anx - D - Milestone report
Annexure - D - send weekly
Mile stone report for CR-
Company name: |  |  |  | Villa Orchids
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 2020-04-30
Note: | Prepare the statement for all the villas in the project.
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Completion of plinth | Completion of RCC | Completion of brickwork and plastering | Completion of stage I | Completion of stage II | Completion of stage III | Completion of stage IV | Date of physical posession
1 | 129 | 3BHK | 1820 | 14.08.189 | 10.12.18 | 14.08.19
2 | 130 | 3BHK | 1820 | 14.08.19 | 10.12.18 | 14.08.19
3 | 136 | 3BHK | 1820 | 01.03.19 | 01.03.19 | 25.07.19
4 | 107 | 3BHK | 1820 | 01.08.19 | 01.12.18/ | 04.09.19
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69

## Anx - E2 - work done & billed
Annexure - E2 - work completed and bill raised -send on the last Saturday of the month. | [14 empty] | 0
Name of contractor: |  |  |  | M Venakt raju
Company name: |  |  |  | MVR constructins
Project name: |  |  |  | VOCLLP | [7 empty] | sx+
Date: |  |  |  | 2020-05-30
Note: | Enter vlaue 1 if work is completed and billed. Enter 0 otherwise. This statement must match billing database.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100 |  |  | 0
S No | Villa no. | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | GST | Construction contract value | Value of work done | Advance Paid | Advance adjusted
1 | 129 | 3BHK | 1820 | 14.08.19 |  |  | 1 | 1 | 1 | 55 | 690 | 18 | 1481844 | 815014.2 |  | 0
2 | 130 | 3BHK | 1820 | 14.08.19 |  |  | 1 | 1 | 1 | 55 | 690 | 18 | 1481844 | 815014.2 |  | 0
3 | 136 | 3BHK | 1820 | 01.03.19 |  |  | 1 | 1 | 1 | 55 | 690 | 18 | 1481844 | 815014.2 |  | 0
4 | 107 | 3BHK | 1820 | 01.08.19 |  |  | 1 | 1 |  | 45 | 690 | 18 | 1481844 | 666829.8 |  | 0
5 | 201 | 3BHK | 1820 | 02.05.18 | 1 | 1 | 1 | 1 | 1 | 100 | 690 | 18 | 1481844 | 1481844 |  | 0
6 | 202 | 3BHK | 1820 | 03.05.18 | 1 | 1 | 1 | 1 | 1 | 100 | 690 | 18 | 1481844 | 1481844 |  | 0
7 | 203 | 3BHK | 1820 | 01.08.18 | 1 | 1 | 1 | 1 | 1 | 100 | 690 | 18 | 1481844 | 1481844 |  | 0
8 | 204 | 3BHK | 1820 | 01.08.18 | 1 | 1 | 1 | 1 | 1 | 100 | 690 | 18 | 1481844 | 1481844 |  | 0
9 | 100 | 3BHK | 1820 | 18.06.18 | 1 | 1 | 1 | 1 | 1 | 100 | 690 | 18 | 1481844 | 1481844 |  | 0
| 101 | 3BHK | 1820 | 18.06.19 | 1 | 1 | 1 | 1 |  | 90 | 691 | 18 | 1483991.6 | 1335592.44
10 | 83 | 3BHK | 1940 | 01.08.19 | 0 | 1 | 1 | 1 | 1 | 80 | 690 | 18 | 1579548 | 1263638.4 |  | 0
11 | 96 | 3BHK | 1820 | 18.06.18 | 1 | 1 | 1 | 1 |  | 90 | 690 | 18 | 1481844 | 1333659.6 |  | 0
13 | 127 | 3BHK | 1820 | 15.12.19 | [5 empty] | 0 | 690 | 18 | 1481844 | 0 |  | 0
14 | 128 | 3BHK | 1820 | 19.12.19 |  |  | 1 |  |  | 25 | 690 | 18 | 1481844 | 370461 |  | 0
15 | 196 | 3BHK | 1585 | 01.12.19 |  |  | 1 |  |  | 25 | 690 | 18 | 1290507 | 322626.75 |  | 0
|  | Total | 27185 |  | 7 | 8 | 14 | 12 | 9 | 68 | 690.0667 | 18 | 22136174.6 | 15147070.59 | 0 | 0

## Anx - E1 -Estimate of work done
Annexure - E1 - Details of partial work done and not yet billed - send on the last Saturday of the month-
Name of contractor: |  |  |  | M Venakt raju
Company name: |  |  |  | MVR Construction
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 2020-05-30
Note: | Enter value beween 1&100 as approximate pecentage of work completed- Enter 0 where work is completed and billed.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | Construction contract value | Value of work done
1 | 129 | 3BHK | 1820 | 14.08.19 |  |  | 0 |  | 0 | 0 | 690 | 1255800 | 0
2 | 130 | 3BHK | 1820 | 14.08.19 |  |  |  | 0 | 0 |  | 690 | 1255800 | 0
3 | 136 | 3BHK | 1820 | 01.03.19 |  |  |  |  | 0 | 0 | 690 | 1255800 | 0
4 | 107 | 3BHK | 1820 | 01.08.19 |  |  |  |  | 100 | 10 | 690 | 1255800 | 125580
5 | 201 | 3BHK | 1820 | 02.05.18 | [5 empty] | 0 | 690 | 1255800 | 0
6 | 202 | 3BHK | 1820 | 03.05.18 |  |  |  |  | 0 | 0 | 690 | 1255800 | 0
7 | 203 | 3BHK | 1820 | 01.08.18 |  |  |  |  | 0 | 0 | 690 | 1255800 | 0
8 | 204 | 3BHK | 1820 | 01.08.18 |  |  |  |  | 0 | 0 | 690 | 1255800 | 0
9 | 100 | 3BHK | 1820 | 18.06.18 | [5 empty] | 0 | 690 | 1255800 | 0
10 | 83 | 3BHK | 1940 | 01.08.19 | [5 empty] | 0 | 690 | 1338600 | 0
11 | 101 | 3BHK | 1820 | 01.08.18 |  |  |  |  | 0 | 0 | 690 | 1255800 | 0
12 | 96 | 3BHK | 1820 | 18.06.18 |  |  |  |  | 100 | 10 | 690 | 1255800 | 125580
13 | 127 | 3BHK | 1820 | 15.12.19 |  |  |  | 0 |  | 0 | 690 | 1255800 | 0
14 | 128 | 3BHK | 1820 | 19.12.19 | [5 empty] | 0 | 690 | 1255800 | 0
15 | 196 | 3BHK | 1585 | 01.12.19 |  |  | 0 |  | 100 | 10 | 690 | 1093650 | 109365
|  | Total | 21960 |  | #DIV/0! | #DIV/0! | 0 | 0 | 22.2222 | 1.8182 | 690 | 15152400 | 360525

## Anx - F -Summary of accounts
Annexure - F - Summary of accounts -send on the last Saturday of the month.
Name of contractor: |  | M Venkat raju
Company name: |  | MVR Construction
Project name: |  | VOCLLP
Date: |  | 2020-05-30
S No | Summary - of credits | Amount
1 | Work completed & billed | 15147070.59
2 | Unbilled amount | 360525
3 | Mobilization advance paid | 0
4 | Payment for increase in rate form ___ to ____
5 | Payment for increase in rate form ___ to ____
6 | Other credits
7 | Club house - billed value
8 | Club house - unbilled value - approx.
9
10
| Total A | 15507595.59
S No | Summary - of debits | Amount
1 | Mobilization advance adjusted | 0
2 | Amount paid | 14858645
3 | Other debits
4
5
6
7
8
9
10
| Total B | 14858645
| Net payable to contractor (A-B) | 648950.59