## Anx - A - Attendance details
Annexure - A - Send Weekly
Details of labour charges
Name of contractor: |  | A Chadrakanth
Company name: |  | Rohan Constructions
Project name: |  | VOC
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Work Type | Worker Type | Quantity | Rate | Amount
1 | Civil work | Mason |  | 575 | 0
2 | Civil work | Male helper |  | 400 | 0
3 | Civil work | Female helper |  | 350 | 0
4 | RCC work | Mason |  | 550 | 0
5 | RCC work | Male helper |  | 400 | 0
6 | RCC work | Female helper |  |  | 0
7 | Earth work | Mason |  |  | 0
8 | Earth work | Male helper |  |  | 0
9 | Earth work | Female helper |  |  | 0
10 | Electrician | Mason |  |  | 0
11 | Electrician | Male helper |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
| Total |  |  |  | 0
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - B - Hire charges
Annexure - B - Send Weekly
Details of hire charges
Name of contractor: |  | A Chadrakanth
Company name: |  | Rohan Constructions
Project name: |  | VOC
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Equipment Type | Quantity | Rate | Units | Amount
1 |  |  |  | Hour | 0
2 |  |  |  | Hour | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
| Total |  |  |  | 0
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - C - Material received
Annexure - C - send weekly
Details of magterial received
Name of contractor: |  | A Chadrakanth
Company name: |  | Rohan constructions
Project name: |  | VOC
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Material type | Received date | Inward no. | Quantity | Units | Rate | Amount
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15
16
17
18
19
20
21
22
23
24 | [6 empty] | 0
| Total | [5 empty] | 0
Payment approved by MD:
Prepared by: |  |  |  | Approved by: |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - D - Milestone report
Annexure - D - send weekly
Mile stone report for CR-
Company name: |  |  |  | Villa Orchids
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 2020-04-30
Note: | Prepare the statement for all the villas in the project.
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Completion of plinth | Completion of RCC | Completion of brickwork and plastering | Completion of stage I | Completion of stage II | Completion of stage III | Completion of stage IV | Date of physical posession
1 | 90 | 3BHK | 1940 | 2017-11-21 | 2018-02-16 | 2018-07-18 | 2019-01-03 | 2018-01-18 | 2019-06-06
2 | 91 | 3BHK | 1940 | 2017-11-21 | 2018-02-14 | 2018-06-12 | 2018-11-01 | 2019-01-05 | 2019-02-23 | 2019-06-01 | 2019-09-15
3 | 119 | 3BHK | 1820 | 2018-12-01 | 2018-11-01 | 2018-12-30 | 2018-03-23 | 2019-07-01
4 | 220 | 3BHK | 1820 | 2019-01-24 | 2019-01-08 | 2019-07-31
5 | 221 | 3BHK | 1820 | 2019-01-24 | 2019-01-08 | 2019-01-20
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69

## Anx - E1 -Estimate of work done
Annexure - E1 - Details of partial work done and not yet billed - send on the last Saturday of the month-
Name of contractor: |  |  |  | A Chandrakanth
Company name: |  |  |  | Rohan construtions
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 2020-05-30
Note: | Enter value beween 1&100 as approximate pecentage of work completed- Enter 0 where work is completed and billed.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | Construction contract value | Value of work done
1 | 12 | 3BHK | 1940 | 2019-09-01 | 0 | 0 | 0 | 0 | 100 | 10 | 320 | 620800 | 62080
2 | 131 | 3BHK | 1820 | 2019-11-12 |  |  | 0 | 100 | 100 | 30 | 320 | 582400 | 174720
3 | 256 | 3BHK | 1820 | 2019-12-12 |  |  | 0 | 0 | 100 | 10 | 320 | 582400 | 58240
4 | 258 | 3BHK | 1820 | 26.11.19 |  |  | 100 | 100 | 100 | 55 | 320 | 582400 | 320320
5 | [9 empty] | 0 |  | 0 | 0
6 | [9 empty] | 0 |  | 0 | 0
7 | [9 empty] | 0 |  | 0 | 0
52 | [9 empty] | 0 |  | 0 | 0
53 | [9 empty] | 0 |  | 0 | 0
54 | [9 empty] | 0 |  | 0 | 0
55 | [9 empty] | 0 |  | 0 | 0
56 | [9 empty] | 0 |  | 0 | 0
57 | [9 empty] | 0 |  | 0 | 0
58 | [9 empty] | 0 |  | 0 | 0
94 | [9 empty] | 0 |  | 0 | 0
95 | [9 empty] | 0 |  | 0 | 0
96 | [9 empty] | 0 |  | 0 | 0
97 | [9 empty] | 0 |  | 0 | 0
98 | [9 empty] | 0 |  | 0 | 0
99 | [9 empty] | 0 |  | 0 | 0
100 | [9 empty] | 0 |  | 0 | 0
101 | [9 empty] | 0 |  | 0 | 0
102 | [9 empty] | 0 |  | 0 | 0
103 | [9 empty] | 0 |  | 0 | 0
104 | [9 empty] | 0 |  | 0 | 0
105 | [9 empty] | 0 |  | 0 | 0
106 | [9 empty] | 0 |  | 0 | 0
107 | [9 empty] | 0 |  | 0 | 0
108 | [9 empty] | 0 |  | 0 | 0
109 | [9 empty] | 0 |  | 0 | 0
110 | [9 empty] | 0 |  | 0 | 0
|  | Total | 7400 |  | 0 | 0 | 25 | 50 | 100 | 3.3871 | 320 | 2368000 | 615360

## Anx - E2 - work done & billed
Annexure - E2 - work completed and bill raised -send on the last Saturday of the month. | [14 empty] | 0
Name of contractor: |  |  |  | A Chandrakanth
Company name: |  |  |  | Rohan construction
Project name: |  |  |  | VOC
Date: |  |  |  | 2020-05-30
Note: | Enter vlaue 1 if work is completed and billed. Enter 0 otherwise. This statement must match billing database.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100 |  |  | 0
S No | Villa no. | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | GST | Construction contract value | Value of work done | Advance Paid | Advance adjusted
1 | 12 | 3BHK | 1940 | 2019-09-01 |  |  | 1 | 1 |  | 45 | 320 | 18 | 732544 | 329644.8 |  | 0
2 | 131 | 3BHK | 1820 | 2019-11-12 |  |  | 1 |  |  | 25 | 320 | 18 | 687232 | 171808 |  | 0
3 | 256 | 3BHK | 1820 | 2019-11-12 |  |  | 1 | 1 |  | 45 | 320 | 18 | 687232 | 309254.4 |  | 0
4 | 258 | 3BHK | 1820 | 2019-11-26 |  |  | 1 |  |  | 25 | 320 | 18 | 687232 | 171808 |  | 0
5 | [9 empty] | 0 | 320 | 18 | 0 | 0 |  | 0
6 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
7 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
8 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
9 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
10 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
11 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
12 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
13 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
14 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
15 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
16 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
17 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
18 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
19 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
20 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
21 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
22 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
23 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
24 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
25 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
26 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
27 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
28 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
29 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
30 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
31 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
32 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
33 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
|  | Total | 7400 |  | 0 | 0 | 4 | 2 | 0 | 4.2424 | 320 | 18 | 2794240 | 982515.2 | 0 | 0

## Anx - F -Summary of accounts
Annexure - F - Summary of accounts -send on the last Saturday of the month.
Name of contractor: |  | A Chandrakanth
Company name: |  | Rohan constructions
Project name: |  | VOC
Date: |  | 2020-05-30
S No | Summary - of credits | Amount
1 | Work completed & billed | 982515.2
2 | Unbilled amount | 615360
3 | Mobilization advance paid | 0
4 | Payment for increase in rate form ___ to ____
5 | Payment for increase in rate form ___ to ____
6 | Other credits
7 | Club house - billed value
8 | Club house - unbilled value - approx.
9
10
| Total A | 1597875.2
S No | Summary - of debits | Amount
1 | Mobilization advance adjusted | 0
2 | Amount paid | 1764950
3 | Other debits
4
5
6
7
8
9
10
| Total B | 1764950
| Net payable to contractor (A-B) | -167074.8