## Anx - A - Attendance details
Annexure - A - Send Weekly
Details of labour charges
Name of contractor: |  | MD Masuddun
Company name: |  | VOCLLP
Project name: |  | VOC
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Work Type | Worker Type | Quantity | Rate | Amount
1 | Civil work | Mason | 12 | 575 | 6900
2 | Civil work | Male helper | 12 | 400 | 4800
3 | Civil work | Female helper |  | 350 | 0
4 | RCC work | Mason |  | 575 | 0
5 | RCC work | Male helper |  | 400 | 0
6 | RCC work | Female helper |  |  | 0
7 | Earth work | Mason |  |  | 0
8 | Earth work | Male helper |  |  | 0
9 | Earth work | Female helper |  |  | 0
10 | Electrician | Mason |  |  | 0
11 | Electrician | Male helper |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
| Total |  |  |  | 11700
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - B - Hire charges
Annexure - B - Send Weekly
Details of hire charges
Name of contractor: |  | MD Masuddun
Company name: |  | VOCLLP
Project name: |  | VOC
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Equipment Type | Quantity | Rate | Units | Amount
1 |  |  |  | Hour | 0
2 |  |  |  | Hour | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
| Total |  |  |  | 0
Payment approved by MD:
Prepared by: |  |  |  |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - C - Material received
Annexure - C - send weekly
Details of magterial received
Name of contractor: |  | MD Masuddun
Company name: |  | voc LLP
Project name: |  | VOC
Date: |  | 2020-07-24
Period |  | From: | 2020-07-17 | To: | 2020-07-24
Sl. No. | Material type | Received date | Inward no. | Quantity | Units | Rate | Amount
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15
16
17
18
19
20
21
22
23
24 | [6 empty] | 0
| Total | [5 empty] | 0
Payment approved by MD:
Prepared by: |  |  |  | Approved by: |  | MDs approval
Name | A Suresh
Date | 2020-07-24

## Anx - D - Milestone report
Annexure - D - send weekly
Mile stone report for CR-
Company name: |  |  |  | Villa Orchids
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 24.10.19
Note: | Prepare the statement for all the villas in the project.
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Completion of plinth | Completion of RCC | Completion of brickwork and plastering | Completion of stage I | Completion of stage II | Completion of stage III | Completion of stage IV | Date of physical posession
1 | 102 | 3BHK | 1820 | 2018-06-26 | 2019-02-15 | 2019-08-21
2 | 103 | 3BHK | 1820 | 2019-06-26 | 2019-02-05
3 | 127 | 3BHK | 1820 | 2018-06-06 | 2019-06-06
4 | 128 | 3BHK | 1820 | 2018-06-09 | 2019-06-17
5 | 124 | 3BHK | 1820 | 2019-09-01 | 2019-01-08 | 2019-01-20
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69

## Anx - E1 -Estimate of work done
Annexure - E1 - Details of partial work done and not yet billed - send on the last Saturday of the month-
Name of contractor: |  |  |  | MD Masuddun
Company name: |  |  |  | MD Masuddun
Project name: |  |  |  | VOCLLP
Date: |  |  |  | 2020-06-06
Note: | Enter value beween 1&100 as approximate pecentage of work completed- Enter 0 where work is completed and billed.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100
S No | Villa no- | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | Construction contract value | Value of work done
1 | 102 | 3BHK | 1820 | 2019-02-02 | 0 | 65 |  | 90 |  | 34.25 | 690 | 1255800 | 430111.5
2 | 103 | 3BHK | 1820 | 2019-02-02 |  | 65 |  | 50 |  | 26.25 | 690 | 1255800 | 329647.5
3 | 127 | 3BHK | 1820 | 2019-02-02 |  | 70 |  | 50 |  | 27.5 | 690 | 1255800 | 345345
4 | 128 | 3BHK | 1820 | 2019-02-02 |  | 70 |  |  |  | 17.5 | 690 | 1255800 | 219765
5 | 124 | 3BHK | 1820 | 2019-02-02 |  |  |  | 90 |  | 18 | 690 | 1255800 | 226044
6 | 184 | 3BHK | 1585 | 2019-02-03 |  |  |  | 95 |  | 19 | 690 | 1093650 | 207793.5
22 | [9 empty] | 0 |  | 0 | 0
23 | [9 empty] | 0 |  | 0 | 0
24 | [9 empty] | 0 |  | 0 | 0
25 | [9 empty] | 0 |  | 0 | 0
66 | [9 empty] | 0 |  | 0 | 0
67 | [9 empty] | 0 |  | 0 | 0
68 | [9 empty] | 0 |  | 0 | 0
69 | [9 empty] | 0 |  | 0 | 0
70 | [9 empty] | 0 |  | 0 | 0
98 | [9 empty] | 0 |  | 0 | 0
99 | [9 empty] | 0 |  | 0 | 0
100 | [9 empty] | 0 |  | 0 | 0
101 | [9 empty] | 0 |  | 0 | 0
102 | [9 empty] | 0 |  | 0 | 0
103 | [9 empty] | 0 |  | 0 | 0
104 | [9 empty] | 0 |  | 0 | 0
105 | [9 empty] | 0 |  | 0 | 0
106 | [9 empty] | 0 |  | 0 | 0
107 | [9 empty] | 0 |  | 0 | 0
108 | [9 empty] | 0 |  | 0 | 0
109 | [9 empty] | 0 |  | 0 | 0
110 | [9 empty] | 0 |  | 0 | 0
|  | Total | 10685 |  | 0 | 67.5 | #DIV/0! | 75 | #DIV/0! | 5.0893 | 690 | 7372650 | 1758706.5

## Anx - E2 - work done & billed
Annexure - E2 - work completed and bill raised -send on the last Saturday of the month. | [14 empty] | 0
Name of contractor: |  |  |  | MD Masuddun
Company name: |  |  |  | VOCLLP
Project name: |  |  |  | VOC
Date: |  |  |  | 2020-06-06
Note: | Enter vlaue 1 if work is completed and billed. Enter 0 otherwise. This statement must match billing database.
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100 |  |  | 0
S No | Villa no. | Type (2, 3, 4BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Rate per sft | GST | Construction contract value | Value of work done | Advance Paid | Advance adjusted
1 | 102 | 3BHK | 1820 | 2019-02-02 |  |  | 1 |  | 0 | 25 | 690 | 18 | 1481844 | 358934 |  | 0
2 | 103 | 3BHK | 1820 | 2019-02-02 |  |  | 1 |  |  | 25 | 690 | 18 | 1481844 | 358934 |  | 0
3 | 127 | 3BHK | 1820 | 2019-02-02 |  |  | 1 |  |  | 25 | 690 | 18 | 1481844 | 341778 |  | 0
4 | 128 | 3BHK | 1820 | 2019-02-02 |  |  | 1 |  |  | 25 | 690 | 18 | 1481844 | 329160 |  | 0
5 | 124 | 3BHK | 1820 | 2019-02-02 | [5 empty] | 0 | 690 | 18 | 1481844 | 0 |  | 0
6 | 184 | 3BHK | 1585 | 2019-02-03 | [5 empty] | 0 | 690 |  | 1093650 |  |  | 0
7 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
8 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
59 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
60 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
61 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
62 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
63 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
64 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
65 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
66 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
67 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
68 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
69 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
70 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
71 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
72 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
73 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
74 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
75 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
110 | [9 empty] | 0 |  |  | 0 | 0 |  | 0
|  | Total | 10685 |  | 0 | 0 | 4 | 0 | 0 | 3.8462 | 690 | 18 | 8502870 | 1388806 | 0 | 0

## Anx - F -Summary of accounts
Annexure - F - Summary of accounts -send on the last Saturday of the month.
Name of contractor: |  | MD Masuddun
Company name: |  | VOCLLP
Project name: |  | VOC
Date: |  | 2020-06-06
S No | Summary - of credits | Amount
1 | Work completed & billed | 1388806
2 | Unbilled amount | 1758706.5
3 | Mobilization advance paid | 0
4 | Payment for increase in rate form ___ to ____
5 | Payment for increase in rate form ___ to ____
6 | Other credits
7 | Club house - billed value
8 | Club house - unbilled value - approx.
9
10
| Total A | 3147512.5
S No | Summary - of debits | Amount
1 | Mobilization advance adjusted | 0
2 | Amount paid | 4261365
3 | Other debits
4
5
6
7
8
9
10
| Total B | 4261365
| Net payable to contractor (A-B) | -1113852.5