## Sheet1
Prepared by: |  | Keerthi Ch
Report Date: |  | 2020-10-09
Site |  | AGH
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is not prepared 3 working days after requisition
165005 | 21/5/2020 | Ms telescopic pole material | Po to be issue
165055 | 2020-11-07 | Red gulmohar trees | Po to be issue
165099 | 24/8/2020 | Swimming pool equipment | Po to be issue
165105 | 26/8/2020 | Pvc water fitting material | Po 70130
165107 | 29/8/2020 | Glass mosaic tiles | Po 70008
165108 | 2020-01-09 | Wires | Po 70102
165109 | 2020-03-09 | Bombay nails | Po 70261
165110 | 2020-03-09 | Plastic gampa | Po 70260
165111 | 2020-01-09 | A4 paper bundles | Po 70143
List of requisitions Where PO/WO is prepared and items have not been received at site
52963 | 01.05.20 | Batoom Tiles | Collect from SSLLP
52981 | 13.05.20 | MS Gate | Collect from SSLLP
165004 | 21.05.20 | Carpet Lawm | This week delivery
165006 | 21.05.2020 | L angle frame | This week delivery
165014 | 3.06.2020 | Gulmohar trees | This week delivery
165075 | 30/7/2020 | Black granite | Collect from SSLLP
165077 | 31.07.20 | Al windows | Collect from SSLLP
165080 | 6.08.20 | MS railing | Collect from SSLLP
165082 | 6.08.20 | NON return valve | This week delivery
165087 | 11.08.20 | MS gate & railing | Collect from SSLLP
165095 | 19/8/20 | Service saddle | This week delivery
165102 | 26/8/2020 | Villa cpvc | This week delivery
165103 | 26/8/2020 | Villa Pvc | This week delivery
165104 | 26/8/2020 | eco drain material | This week delivery