## SOVLLP
Prepared by: |  | Keerthi
Report Date |  | 2020-10-09
Site |  | SOV LLP
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
155949 | 27/8/20 | Linoleum flooring | Estimate to be prepare
155950 | 27/8/20 | Carpet flooring | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
155830 | 27.06.20 | Executive bag | Collect from SSLLP
155831 | 27.06.20 | Executive bag | Online Purchase
155905 | 27.07.20 | Syphone set | This week delivery
155912 | 30.07.20 | Syphone set | Pick it from SSLLP
155937 | 13/8/20 | Lawn mover | This week delivery
155955 | 27/8/20 | FP isolaters | This week delivery