## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2020-12-26
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
180501 | 2020-12-07 | GI Nipple | PO 73072
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
99923 | 2.11.20 | Sliding windows | Pick up from SSLLP
99940 | 11.11.20 | Generator AMF pannel | Approved by MD, require association approval, awaiting
99947 | 16.11.20 | Main limit switch (Lift part) | Estimate with MD for approval
99974 | 7.12.20 | GI U clamps thred type with nuts | Delivered
99989 | 12.12.20 | Sanitary | Delivered
99990 | 12.12.20 | CP Fittings | Delivered
99995 | 14.12.20 | GI PVC Coated | Delivery on Monday
99999 | 16.12.20 | MS Langle | Delivered
180504 | 18.12.20 | Acid | Part delivered balance pick up from SSLLP
180505 | 18.12.20 | Wipro garnet | Part delivered balance pick up from SSLLP
180507 | 19.12.20 | Pannel doors | Pick up from SSLLP
180508 | 19.12.20 | Switches | Delivered
180511 | 19.12.20 | Sanitary | Pick up from SSLLP
180513 | 21.12.20 | Wipro flood lights | Pick up from SSLLP
180514 | 21.12.20 | Enamel paint | Delivered
180515 | 21.12.20 | Jantha paste | Delivered
180516 | 21.12.20 | Ciatern set | Delivered
180517 | 21.12.20 | Roff tiles adhesive | Delivered