## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2020-12-27
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163274 | 2020-12-04 | LED Lights | Note with MD for approval
162375 | 2020-12-04 | LED Lights | Note with MD for approval
163276 | 2020-12-07 | Autometic rebar tying machine | Rates exquiry
163276 | 2020-12-07 | Air blower | Online purchased awaiting for delivery
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163277 | 2020-12-07 | Twisted wire bruch | Monday delivery
163281 | 2020-11-23 | Lizol dust bin covers | Pick up from SSLLP
163266 | 2020-11-23 | Biometric machine battary | Monday delivery
163284 | 2020-12-10 | Glouses | Delivered
163291 | 2020-12-18 | Brown tapes and sissors | Delivered
163292 | 2020-12-19 | Fosroc nitobond | Delivered
163293 | 2020-12-21 | Coffee powder | Monday delivery
163294 | 2020-12-22 | Gum boots and Labour helmets | Monday delivery