## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-02-20
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 2020-11-18 | SS Railing 8 mm toughned glass | Rates comparision with MD for rivision
177287 | 2021-01-13 | Rebars couplers | Rates enquiry
177386 | 2021-02-16 | Sliding windows | Req with MD
177387 | 16.2.21 | Sliding windows | Req with MD
List of requisitions where PO/WO is prepard and items have not been deliverd at site beyond the lead time
177172 | 1.12.20 | 5x3 Z angle templates | Material are in powder coating take the delivery on Monday
177297 | 19.1.21 | Executive bags | Purchased onlie awaiting for delivery
177305 | 21.1.21 | Kitchen dado, country almond , country café tiles | Pick up from MPL/Vista
177315 | 23.1.21 | Bathroom tiles | Pick up from MPL/Vista
177336 | 2.2.21 | Kitchen dado tiles | Pick up from MPL/Vista
177347 | 4.2.21 | Pannel doors, Hinges, Locks | Part material delivered balance Pick up from SSLLP
177349 | 4.2.21 | Tan brown granite | Pick up from SOVLLP
177353 | 5.2.21 | Vitrified tiles | Awaiting to receive from supplier
177359 | 8.2.21 | PVC False ceiling | This is work order remove from this remarks
177360 | 8.2.21 | Bathroom tiles | Awaiting to receive from supplier
177366 | 9.2.21 | Spacers | Pick up from SSLLP
177369 | 10.2.21 | Tan brown granite | Pick up from SOVLLP
177370 | 10.2.21 | PVC False ceiling | This is work order remove from this remarks
177373 | 10.2.21 | PVC Door Y | Pick up from SSLLP
177376 | 12.2.21 | Pannel doors 38''x80'' | Awaiting to receive from supplier
177381 | 13.2.21 | MS Round pipe | Call supplier he will deliver
177382 | 15.2.21 | Air blower | Delivered
177384 | 15.2.21 | Pannel doors 38''x80'' | Awaiting to receive from supplier
177388 | 17.2.21 | Sponges, bombay brooms, janta paste | Pick up from SSLLP
177389 | 17.2.21 | Cleaning material | Pick up from SSLLP
177390 | 17.2.21 | Chalk piece, curing pipe | Pick up from SSLLP