## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-02-20
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163336 | 30.1.21 | Jio dongle | Delivered
163340 | 4.2.21 | Visiting cards | Follow up with Promotions
163363 | 15.2.21 | Tea powder | Delivered
163366 | 16.2.21 | Openwell submersable pump | Po to be issue
163372 | 18.2.21 | Openwell submersable pump | Po to be issue
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163303 | 7.1.21 | MS Material | Speak to the supplier he will arrenge the delivery
163353 | 9.2.21 | Inward stamp, Out ward stamp | Follow up with Admin
163359 | 12.2.21 | RCC Square cover | Speak to the supplier he will arrenge the delivery
163364 | 16.2.21 | Paper full scape | Pick up from suppliers place
163365 | 16.2.21 | Drawing cover | Pick up from suppliers place
163369 | 17.2.21 | MS Boxes | Speak to the supplier he will arrenge the delivery
163369 | 17.2.21 | MS Square rod MS Box pipe | Speak to the supplier he will arrenge the delivery
163370 | 18.2.21 | Bonding agent | Pick up from suppliers place
163371 | 18.2.21 | Fosroc agent | Pick up from suppliers place