## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-02-20
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
180540 | 2020-12-29 | Letter box | Rates enquiry
180630 | 2021-02-11 | Al sliding windows | PO to be issue
180636 | 2021-02-13 | Urinal set | PO to be issue
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
99940 | 11.11.20 | Generator AMF pannel | Quotes to be received from supplier
180536 | 29.12.20 | Luminous board | Pick up from SSLLP
180576 | 13.1.21 | Cistern set | Pick up the material from supplier
180578 | 13.1.21 | Modular kitchen | Material under process
180614 | 2.2.21 | SS Name plate | Work under process
180615 | 2.2.21 | SS Name plate | Work under process
180617 | 16.1.21 | Vitrified tiles | Issue the DC for the qty and send to SSLLP for Billing, these are consumed tiles
180628 | 10.2.21 | Cleaning material | Delivered
180629 | 10.2.21 | Video door phone | Delivered
180631 | 13.2.21 | Wire brush | Delivered
180632 | 13.2.21 | Queen size bed sheet and pillows | Delivered
180633 | 13.2.21 | MMC, 4 pole isolater, DB Boxes | Delivered
180634 | 13.2.21 | Rubber moulded tiles | Delivered