## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estates
Site: |  | 2021-02-20
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
175157 | 21.1.21 | SS Boards | Hold by MD
175187 | 11.2.21 | Sliding windows | Po to be issue
175191 | 12.2.21 | UV Plastisizer sheet | Po to be issue
175192 | 12.2.21 | Box for ms street light pole | Sample to be receive
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175184 | 8.1.21 | Sanitary | Pick up from SSLLP
175189 | 11.2.21 | Sanitary | Pick up from SSLLP
175190 | 11.2.21 | CP fittings | Pick up from SSLLP
175194 | 12.2.21 | Plane false ceiling | Work under process(remove this from remarks)
175195 | 12.2.21 | Sanitary | Pick up from SSLLP
175198 | 13.2.21 | Altek lappum | Pick up from SSLLP
175199 | 15.2.21 | Steel | Co ordinate with supplier for delivery
175202 | 16.2.21 | Shade grass | Supplier will arrenge as per site requirment
175204 | 17.2.21 | Sanitary | Pick up from SSLLP
175205 | 17.2.21 | CP fittings | Pick up from SSLLP