## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-03-27
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163355 | 10.2.21 | Autometic serveice lift | MD to finalise the rates
163357 | 10.2.21 | Autometic passinger lift | PO 75400
163372 | 18.2.21 | Open well submersable pump | Cancelied
163374 | 19.2.21 | Bio metric chargere | No stock with supplier
163397 | 11.3.21 | Auto starter | PO 75832
163400 | 11.3.21 | Autometic cutoff starter | PO 75833
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163384 | 26.2.21 | Gunny bags | Deliverd
163401 | 13.3.21 | Water bubbles | Pick up from SSLLP
163403 | 13.3.21 | 25 sq mm armourd cable | Deliverd
163404 | 13.3.21 | 2'' PVC Pipe | Deliverd
163405 | 16.3.21 | Project folder and fevicol | Pick up from Venkataramana
163406 | 16.3.21 | Mesuring tapes with sprit level | Deliverd
163407 | 18.3.21 | Al serveice wire | Deliverd
163408 | 19.3.21 | Ring binder files | Deliverd