## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-03-27
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
180630 | 2021-02-11 | Al sliding windows | PO to be issue
180636 | 2021-02-13 | Urinal set | PO to be issue
180714 | 17.3.21 | 3 pole MCCB,MCCB with distribution box | Confirmation required from site
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
99940 | 11.11.20 | Generator AMF pannel | Stock to be receive from supplier
180540 | 29.12.21 | Letter box | Work under process
180576 | 13.1.21 | Cistern set | Pick up from supplier place
180633 | 13.2.21 | 4 pole isolater, DB Boxes | Delivered
180646 | 25.2.21 | CP Fittings | Delivered
180658 | 3.3.21 | SS Sink waste coupling | Delivered
180700 | 6.3.21 | Panel doors | Delivered
180712 | 16.3.21 | 4 pole isolater, and switches | Delivered
180715 | 17.3.21 | Rubber paints | Delivered