## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estates
Site: |  | 2021-03-27
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
175157 | 21.1.21 | SS Boards | Hold by MD
175187 | 11.2.21 | Sliding windows | Po to be issue
175191 | 12.2.21 | UV Plastisizer sheet | PO 75285
175192 | 12.2.21 | Box for ms street light pole | Sample to be receive
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175213 | 23.2.21 | Tandoor stone | Delivered
175216 | 23.2.21 | Panel doors | Pick up from SSLLP
175217 | 24.2.21 | Country rosso | Pick up from MPL/VISTA