## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Modi Realty Pocharam LLP(NGH)
Site: |  | 2021-03-27
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
181545 | 17.2.21 | Mouseand brousher stand | Online purchased awaiting for reply
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181556 | 15.3.21 | EWC P trap | Pick up from Praful sanitary