## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-04-03
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Estimate with MD for approval
177297 | 19.01.2021 | Executive bags | Online purchase
177387 | 16.02.2021 | Sliding window | PO 76274
177416 | 22.02.2021 | Rolling shutter | PO 75761
177441 | 09.03.2021 | MS ISMC C channel | PO 75457
177459 | 15.03.2021 | SS Railing 8mm toughness | Cancelled by Site
177460 | 15.03.2021 | SS Railing 8mm toughness | Cancelled by Site
177461 | 15.03.2021 | MS railing | PO 75988
177467 | 15.03.2021 | Sliding window | PO 75691
177476 | 17.03.2021 | SS Railing 8mm glass | PO 76200, 76201
177477 | 17.03.2021 | SS Railing 8mm glass | PO 76202, 76203
177478 | 17.03.2021 | Panel Doors | PO 76158, 76159
177479 | 17.03.2021 | Panel doors | PO 76158, 76159
177480 | 18.03.2021 | UPVC 2.5 track French window with mesh | PO 76192, 76193
177481 | 18.03.2021 | UPVC 2.5 track French window with mesh | PO 76195, 76196
177482 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177483 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177484 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177485 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177486 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177487 | 18.03.2021 | 40amps isolator ,MCBs | PO 75717, 75718
177488 | 18.03.2021 | 40amps isolator ,MCBs | PO 75720, 75721, 75722
177490 | 18.03.2021 | Sliding windows | PO 75741, 76189, 76191
177491 | 18.03.2021 | Grills | PO 76255, 76258
177492 | 18.03.2021 | Wall mixture | Estimate to be prepare
177493 | 18.03.2021 | Wall mixture | Estimate to be prepare
177494 | 19.03.2021 | Sadar ali grey Granite | PO 76103
177495 | 19.03.2021 | Sadar ali grey Granite | PO 76102
177496 | 19.03.2021 | Sliding window | PO 76187, 76188
177497 | 19.03.2021 | Grills | PO to be issue
177498 | 19.03.2021 | Sink & loft Tank | PO 75767
177499 | 19.03.2021 | Sink & loft Tank | PO 75742, 75766
177502 | 19.03.2021 | Sanitary | Estimate to be prepare
177503 | 19.03.2021 | Sanitary | Estimate to be prepare
177509 | 20.3.2021 | Wooden ribbets | PO 75926
177512 | 20.03.2021 | Cu- multi wires | PO 75815, 75816
177513 | 20.03.2021 | Cu- multi wires | PO 75817, 75820
177514 | 20.03.2021 | Door beeding | PO 76073
177516 | 20.03.2021 | Vetrified tiles | Cancelled by Site
177525 | 24.03.2021 | Refrigerator | PO to be issue
177530 | 25.03.2021 | SS railing 8mm glass | Cancelled by Site
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177172 | 01.12.2021 | 5x3 z angle templates | No stock At supplier
177384 | 15.02.2021 | Panel doors ,hinges ,Mortise lock | Pick up from SSLLP
177404 | 24.02.2021 | Grills | Pick up from SSLLP
177428 | 24.02.2021 | Panel doors | Pick up from SSLLP
177447 | 11.03.2021 | Vetrified tiles stained concrete beige,grigio,marfil | Pick up from GMR
177463 | 15.03.2021 | Grill | Pick up from SSLLP
177465 | 15.03.2021 | Grill | Pick up from SSLLP
177507 | 20.03.2021 | Z angle Templates | Pick up from SSLLP
177511 | 20.03.2021 | RCC rings | Delivered
177515 | 20.03.2021 | Main door beeding | Pick up from SSLLP
177527 | 25.03.2021 | Pvc pipe metal box | Pick up from SSLLP
177529 | 25.03.2021 | Sockets ,switches MCB | Pick up from SSLLP
177536 | 27.03.2021 | MS pipe | Supplier Arrange the Material delivered by next week
177539 | 30.03.2021 | GI pipe | Supplier Arrange the Material delivered by next week
177541 | 31.03.2021 | Pannel skin doors | pick up from ssllp
177542 | 31.03.2021 | Pannel skin doors | pick up from ssllp
177543 | 31.03.2021 | Pannel skin doors | pick up from ssllp
177544 | 31.03.2021 | Doors beeding | pick up from ssllp