## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-04-03
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163355 | 10.2.21 | Autometic serveice lift | MD to finalise the rates
163357 | 10.2.21 | Autometic passinger lift | PO 75400
163422 | 25.3.21 | Hand gloves | Samples to be approve
163425 | 26.3.21 | Cups and saucers | Loacl purchase
163431 | 31.3.21 | Submersable pump | PO 76288
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163401 | 13.3.21 | Water bubbles | Delivered
163405 | 16.3.21 | Project folder and fevicol | Pick up from Venkataramana
163409 | 20.3.21 | Engineer safety shoes | Delivered
163418 | 24.3.21 | Curb stone | Delivered
163424 | 26.3.21 | Lemon tea powder | Delivery with in 2 days
163426 | 26.3.21 | Gunny bags | Delivered