## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-04-10
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
180630 | 2021-02-11 | Al sliding windows | PO to be issue
180636 | 2021-02-13 | Urinal set | Not avialable in market
180722 | 2021-03-20 | Wifi cc camera | Online purchase
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
99940 | 11.11.20 | Generator AMF pannel | Stock to be receive from supplier
180540 | 29.12.21 | Letter box | Work under process
180700 | 6.3.21 | Panel doors | Pick up from SSLLP
180726 | 24.3.21 | Wipro lights | Delivered
180733 | 31.3.21 | Water dispenser | Pick up from Aryan Ent
180735 | 31.3.21 | Hob and Chimney | Pick up from supplier
180737 | 31.3.21 | Flush tank hindware | Pick up from supplier
180742 | 3.4.21 | Screws and fishers | Delivered
180743 | 3.4.21 | Nail clamps | Delivered
180744 | 3.4.21 | Wall cutting blades | Pick up from supplier
180747 | 6.4.21 | Stationery material | Delivered
180748 | 6.4.21 | Cleaning material | Delivered