## VOC LLP
Prepared by: | Mounika
Report Date | 17.04.21
Site | Villa Orchids LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
63673 | 31.03.21 | Video Door Phones | Requisition sent for Customer Relation for Approval
List of requisitions Where PO/WO is prepared and items have not received at site
63666 | 16.03.21 | Tan Brown Granite | Pick from SSLLP