## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-04-17
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163357 | 10.2.21 | Autometic passinger lift | PO 75400
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163405 | 16.3.21 | Project folders A1& A2 | Pick up from Venkataramana
163418 | 24.3.21 | Curb stone | Supplier will deliver as per the requirment of site
163426 | 26.3.21 | Gunny bags | Deliverd
163434 | 2.4.21 | Mask | Not avialable in SSLLP
163439 | 7.4.21 | 40 amps isolater | Pick up from SSLLP
163440 | 7.4.21 | First aid box | Pick up from SSLLP