## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-04-17
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | PO to be issue
177297 | 19.01.2021 | Executive bags | Online purchased awaiting for delivery
177479 | 17.3.21 | Panel doors | This requisition qty is added in the PO 76159,76159 check the PO`s throughly
177482 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177483 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177484 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177485 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177486 | 18.03.2021 | Kitchen unit | Estimate to be prepare
177492 | 18.03.2021 | Wall mixture | Estimate to be prepare
177493 | 18.03.2021 | Wall mixture | Estimate to be prepare
177497 | 19.03.2021 | Grills | Part II, PO will be issued as per the schdule
177498 | 19.3.2021 | Sink | PO 75741
177502 | 19.03.2021 | Sanitary | Estimate to be prepare
177503 | 19.03.2021 | Sanitary | Estimate to be prepare
177509 | 20.3.2021 | Wooden ribbets | PO to be issue
177525 | 24.03.2021 | Refrigerator | PO to be issue
177517 | 22.3.21 | False ceiling | PO 75807
177558 | 6.4.21 | Texture | PO 76351
177572 | 12.4.21 | Cable try | PO 76396]
177574 | 12.4.21 | Z angle templates | PO 76509
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177172 | 01.12.2021 | 5x3 z angle templates | Collect from SSLLP
177404 | 24.02.2021 | Grills | Half of the material we received remaining we will pick up from SSLLP next week
177463 | 15.03.2021 | Grill | Half of the material we received remaining we will pick up from SSLLP next week
177465 | 15.03.2021 | Grill | Material is ready we will pickup from SSLLP on this week
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478 | 17.03.2021 | Pannel doors part 1 | Part material delivered
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Work under progress
177488 | 18.03.2021 | MCBs,modular plate ,socket | Work under progress
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177494 | 19.03.2021 | Sadara li Grey Granite | Supplier arrange the material delivered by next week
177495 | 19.03.2021 | Sadara li Grey Granite | Supplier arrange the material delivered by next week
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177499 | 19.03.2021 | Stainless steel sink | Supplier arrange the material delivered by next week
177504 | 19.3.21 | Bison board | Deliverd
177512 | 20.03.2021 | Cu multi wire yellow /red | Half of the material we received remaining we will pick up from SSLLP next week
177513 | 20.03.2021 | Cu multi wire yellow /red | Supplier Arrange the Material delivered by next week
177515 | 20.03.2021 | Main door beeding | Supplier arrange the material delivered by next week
177527 | 25.03.2021 | Pvc pipe metal box | Supplier arrange the material delivered by next week
177529 | 25.03.2021 | Sockets ,switches MCB | Supplier arrange the material delivered by next week
177532 | 26.03.2021 | Tan brown Granite | Supplier Arrange the Material delivered by next week
177541 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week
177542 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week
177543 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week
177544 | 31.03.2021 | Doors beeding | will pick up from SSLLP next week
177552 | 02.04.2021 | Luna ,ultra , Malaysian | As per schdule suppier will deliver the tiles
177559 | 06.04.2021 | Luna ,ultra , Malaysian | As per schdule suppier will deliver the tiles
177560 | 06.04.2021 | Classic dyna | As per schdule suppier will deliver the tiles
177561 | 06.04.2021 | Traventine Romano | As per schdule suppier will deliver the tiles
177562 | 06.04.2021 | Vitrified tiles | As per schdule suppier will deliver the tiles
177563 | 06.04.2021 | Kitchen dado,utility floor tiles | As per schdule suppier will deliver the tiles
177564 | 06.04.2021 | Ms Railing | Supplier Arrange the Material delivered by next week
177565 | 7.4.21 | Urban wood dark | Supplier arrange the material delivered by next week
177568 | 9.4.21 | PVC Pipes material | Deliverd
177569 | 9.4.21 | PVC Pipes material | Deliverd
177573 | 12.4.21 | Main door stopper | Pick up from Sri sai rohit