## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-04-24
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Document is Estimation
177297 | 19.01.2021 | Executive bags | Online purchase
177482 | 18.03.2021 | Kitchen unit | Quotes to be receive
177483 | 18.03.2021 | Kitchen unit | Quotes to be receive
177484 | 18.03.2021 | Kitchen unit | Quotes to be receive
177485 | 18.03.2021 | Kitchen unit | Quotes to be receive
177486 | 18.03.2021 | Kitchen unit | Quotes to be receive
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177497 | 19.03.2021 | Grills | Po to be issue
177502 | 19.03.2021 | Sanitary | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary | Rates to be finalized by MD
177509 | 20.3.2021 | Wooden ribbets | Po is not issue
177517 | 22.03.2021 | False ceiling | Document is Estimation
177525 | 24.03.2021 | Refrigerator | Po to be issue
177577 | 16.04.2021 | Eco drain chamber | Po to be issue
177588 | 17.04.2021 | Waterproofing | Document is Estimation
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177172 | 01.12.2021 | 5x3 z angle templates | No stock At supplier
177404 | 24.02.2021 | Grills | Half of the material we received remaining we will pick up from SSLLP next week
177463 | 15.03.2021 | Grill 2x2 | No stock At SSLLP
177465 | 15.03.2021 | Grill 4x3&others | No stock At SSLLP
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478 | 17.03.2021 | Pannel doors part 1 | Half of the material we received remaining we will pick up from SSLLP next week
177479 | 17.03.2021 | Pannel doors part 1 | Supplier Arrange the material Delivered by next week
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Work under progress
177488 | 18.03.2021 | MCBs,modular plate ,socket | Work under progress
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177491 | 18.03.2021 | Grills | No stock At supplier
177494 | 19.03.2021 | Sadara li Grey Granite | Half of the material we received remaining we will pick up next week
177495 | 19.03.2021 | Sadara li Grey Granite | Supplier arrange the material delivered by next week
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177499 | 19.03.2021 | Stainless steel sink | Supplier arrange the material delivered by next week
177513 | 20.03.2021
177514 | 20.03.2021 | Cu multi wire yellow /red | Supplier Arrange the Material delivered by next week
177515 | 20.03.2021 | Main door beeding | Supplier Arrange the Material delivered by next week
177529 | 25.03.2021 | Main door beeding | Half of the material we received remaining we will pick up from SSLLP next week
177541 | 31.03.2021 | Sockets ,switches MCB | Half of the material we received remaining we will pick up from SSLLP next week
177542 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week
177543 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week
177544 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week
177546 | 01.04.2021 | Doors beeding | will pick up from SSLLP next week
177547 | 01.04.2021 | PVC false ceiling wenge | Supplier arrange the material Delivered by next Week
177559 | 06.04.2021 | PVC false ceiling white | Supplier arrange the material Delivered by next Week
177560 | 06.04.2021 | Luna ,ultra , Malaysian | Supplier Arrange the Material delivered by next week
177561 | 06.04.2021 | Classic dyna | Half of the material we received remaining material supplier arrange the material delivered by next week
177562 | 06.04.2021 | Traventine Romano | Supplier Arrange the Material delivered by next week
177563 | 06.04.2021 | Vitrified tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177564 | 06.04.2021 | Kitchen dado,utility floor tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177565 | 07.04.2021 | Ms Railing | No stock At supplier
177569 | 09.04.2021 | Urban wood dark | Material In Transit
177572 | 12.04.2021 | PVC Pipes material | Half of the material we received remaining we will pick up from SSLLP next week
177582 | 17.04.2021 | Cable Tray ,Anchor bolts & Tread rods | Supplier Arrange the Material delivered by next week
177583 | 17.04.2021
177584 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Supplier arrange the material delivered by next week
|  | Pvc pipes | Half of the material we received remaining we will pick up from SSLLP next week
|  | Inwall tanks | No stock At supplier
177583 | 17.04.2021
|  | Pvc pipes | Half of the material we received remaining we will pick up from SSLLP next week