## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estates
Site: |  | 2021-04-24
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
175157 | 21.1.21 | SS Boards | Hold by MD
175187 | 11.2.21 | Sliding windows | PO to be issue
175250 | 10.4.21 | Parking benches | Estimate to be prepare
175252 | 10.4.21 | MS Square pipes | Cancelled
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
172194 | 2021-02-12 | Plane false ceiling | PO to be issue
175242 | 2021-03-17 | Video door phones | Pick up from suppliers place
175243 | 2021-03-20 | Bison board | Pick up from suppliers place
175246 | 2021-03-27 | Panel doors | Pick up from SSLLP
175249 | 2021-04-05 | Chairs | Draft PO with MD for approval