## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Modi Realty Pocharam LLP(NGH)
Site: |  | 2021-04-24
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181558 | 19.3.21 | Visiting cards | Promotions to follow up
181559 | 27.3.21 | Curb stone | Pick up from supplier
181560 | 2.4.21 | MS Gate | Pick up from supplier