## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-05-03
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Estimate to be prepare
177297 | 19.01.2021 | Executive bags | Online purchase
177482 | 18.03.2021 | Kitchen unit | Quotes to be receive
177483 | 18.03.2021 | Kitchen unit | Quotes to be receive
177484 | 18.03.2021 | Kitchen unit | Quotes to be receive
177485 | 18.03.2021 | Kitchen unit | Quotes to be receive
177486 | 18.03.2021 | Kitchen unit | Quotes to be receive
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177497 | 19.03.2021 | Grills | Po to be issue
177502 | 19.03.2021 | Sanitary | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary | Rates to be finalized by MD
177509 | 20.3.2021 | Wooden ribbets | Po is not issue
177517 | 22.03.2021 | False ceiling | Document is Estimation
177525 | 24.03.2021 | Refrigerator | Po to be issue
177577 | 16.04.2021 | Eco drain chamber | Po to be issue
177588 | 17.04.2021 | Waterproofing | Document is Estimation
177593 | 21.04.2021 | Grey Stone Macherla | Reqisition send to MDS Approval
177603 | 24.04.2021 | Cinder coal Ash | Enquiry in market
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177172 | 01.12.2021 | 5x3 z angle templates | No stock At supplier
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177404 | 24.02.2021 | Grills | Pick up from SSLLP
177447 | 11.03.2021 | Concrete grigio | Pick up from SSLLP
177463 | 15.03.2021 | Grill 2x2 | Pick up from SSLLP
177465 | 15.03.2021 | Grill 4x3&others | Pick up from SSLLP
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478 | 17.03.2021 | Pannel doors part 1 | Supplier will deliver as per the given schdule
177479 | 17.03.2021 | Pannel doors part 1 | Supplier will deliver as per the given schdule
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Supplier will deliver as per the given schdule
177488 | 18.03.2021 | MCBs,modular plate ,socket | Supplier will deliver as per the given schdule
177490 | 18.03.2021 | Sliding window UPVC | Supplier will deliver as per the given schdule
177491 | 18.03.2021 | Grills | Pick up from SSLLP
177494 | 19.03.2021 | Sadara li Grey Granite | Supplier arrange the material delivered by next week
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177499 | 19.03.2021 | Stainless steel sink | PO reissuing to another supplier
177513 | 20.03.2021 | Cu multi wires ,tv ,spring wire | Supplier will deliver as per the given schdule
177514 | 20.03.2021 | Main door beeding | Supplier will deliver as per the given schdule
177515 | 20.03.2021 | Main door beeding | Supplier will deliver as per the given schdule
177541 | 31.03.2021 | Pannel skin doors | Part material delivered, balance as per the schdule supplier will deliver
177543 | 31.03.2021 | Pannel skin doors | Part material delivered, balance as per the schdule supplier will deliver
177544 | 31.03.2021 | Doors beeding | Supplier will deliver as per the given schdule
177547 | 01.04.2021 | PVC false ceiling white | Work under progress
177559 | 06.04.2021 | Luna ,ultra , Malaysian | Pick up from SSLLP
177560 | 06.04.2021 | Classic dyna | Delivered
177561 | 06.04.2021 | Traventine Romano | Delivered
177562 | 06.04.2021 | Vitrified tiles | As per the schdule supplier will deliver
177563 | 06.04.2021 | Kitchen dado,utility floor tiles | As per the schdule supplier will deliver
177564 | 06.04.2021 | Ms Railing | Work under progress
177565 | 07.04.2021 | Urban wood dark | Delivered
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Supplier will deliver as per the given schdule
177583 | 17.04.2021 | Pvc pipes | Supplier will deliver as per the given schdule
177584 | 17.04.2021 | Inwall tanks | Supplier will deliver as per the given schdule
177594 | 21.04.2021 | Tan brown Granite | Pick up from SSLLP
177596 | 23.04.2021 | General items | Pick up from SSLLP
177598 | 23.04.2021 | Bath room tiles | As per the schdule supplier will deliver
177599 | 24.04.2021 | Grigio serena, concrete beige & concrete grigio | As per the schdule supplier will deliver
177605 | 26.04.2021 | Pens | Delivered
177606 | 26.04.2021 | Acid ,Dettol, lisol | Delivered
177608 | 26.04.2021 | Pvc pipe 1.2 mm | Delivered
177609 | 27.04.2021 | Flexible pipe | As per the schdule supplier will deliver