## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Modi Realty Pocharam LLP(NGH)
Site: |  | 2021-05-03
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
181564 | 2021-04-19 | Cement | PO 76754
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181558 | 19.3.21 | Visiting cards | Promotions to follow up
181560 | 2.4.21 | MS Gate | Pick up from supplier
181565 | 17.4.21 | Plastic file | Delivered
181567 | 26.4.21 | Safety shoes | Pick up from supplier
181569 | 29.4.21 | Handwash | Pick up from SSLLP
181570 | 29.4.21 | Consumables | Pick up from SSLLP
181571 | 29.4.21 | Medical Kit | Pick up from SSLLP