## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-05-03
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
180630 | 2021-02-11 | Al sliding windows | PO to be issue
180722 | 2021-03-20 | Wifi cc camera | PO 76719
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180700 | 6.3.21 | Panel doors | Part qty deliver balance pick up from SSLLP
180735 | 31.3.21 | Hob and Chimney | Co ordinate with supplier
180766 | 19.4.21 | UPVC Sliding windows | Work under process
180771 | 20.4.21 | MS Langles | Co ordinate with supplier
180776 | 28.4.21 | Laptop bags | PO to be issue
180777 | 28.4.21 | Enamel paints | Pick up from SSLLP
180778 | 28.4.21 | Indian wc pvc flush pvc long bend | Deliverd
180780 | 29.4.21 | Wipro garnet light | Deliverd