## VOC LLP
Prepared by: | Mounika
Report Date | 07.05.21
Site | Villa Orchids LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
63673 | 31.03.21 | Video Door Phones | Requisition sent for Customer Relation for Approval
List of requisitions Where PO/WO is prepared and items have not received at site
63688 | 30.04.21 | Flush Plates Screws | Pick from Supplier