## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-05-08
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163444 | 2021-04-17 | Sanitizer | Cancell this requisition we are not keeping any stock for sanitizers
163459 | 2021-04-26 | Calm shell cards | Online purchase
163463 | 2021-04-27 | 2' tube lights | Requisition not found send it again
163464 | 2021-04-27 | Safety shoes | Requisition not found send it again
163466 | 2021-04-28 | Steel 8,10 mm | PO 77125
163467 | 2021-04-29 | Foot valve | Searching in market
163473 | 2021-05-04 | 1.75 HP Cutter pump | PO 77085
163469 | 2021-04-29 | 4'' Membrence | PO 76920
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163357 | 2021-02-10 | Autometic passenger lift | Work under process
163405 | 2021-03-16 | Project folders A1&A2 | Pick up from Venkataramana Stationery
163418 | 2021-03-24 | Curb stone | Deliverd
163434 | 2021-03-24 | Mask | Cloth mask is not avialable at SSLLP, will let you know once avialable
163441 | 2021-04-17 | 2.5 sqmm al serveice wire | Deliverd
163442 | 2021-04-17 | Spray paint | Pick up from Ganji Venkanna
163447 | 2021-04-21 | Electrical material | Deliverd
163449 | 2021-04-21 | MS Light stand | Deliverd
163455 | 2021-04-24 | CPVC material | Deliverd
163457 | 2021-04-24 | Orange jackets | Deliverd
163460 | 2021-04-27 | Camera | Po to be issue
163461 | 2021-04-27 | Key chain rings | Deliverd