## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-05-15
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Document is Estimation
177479 | 20.03.2021 | Panel doors | Po to be issue
177482 | 18.03.2021 | Kitchen unit | Quotes to be receive
177483 | 18.03.2021 | Kitchen unit | Quotes to be receive
177484 | 18.03.2021 | Kitchen unit | Quotes to be receive
177485 | 18.03.2021 | Kitchen unit | Quotes to be receive
177486 | 18.03.2021 | Kitchen unit | Quotes to be receive
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177497 | 19.03.2021 | Grills | Po to be issue
177502 | 19.03.2021 | Sanitary | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary | Rates to be finalized by MD
177525 | 24.03.2021 | Refrigerator | Po to be issue
177588 | 17.04.2021 | Waterproofing | Po to be issue
177593 | 21.04.2021 | Grey Stone Macherla | Po to be issue
177603 | 24.04.2021 | Cinder coal Ash | Enquiry in market
177614 | 28.04.2021 | Clamshell Cards | Online purchase
177629 | 04.05.2021 | Hp lazer set , Canon LBP | Requisition send to MD s Approval
177630 | 04.05.2021 | Grills | Requisition send to MD sApproval
177632 | 05.05.2021 | Tread rods ,Anchor bolt | Requisition send to MD s Approval
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177404 | 24.02.2021 | Grills 2x2 | Half of the material we received remaining we will pick up from SSLLP next week
177447 | 11.03.2021 | Concrete grigio | Material is ready At GMR we will pick up on next Monday
177463 | 15.03.2021 | Grill 4x3& 5x3 | Half material we received remaining supplier arrange in the material delivered by next week
177465 | 15.03.2021 | Grill 3x4,4x4,5x3 | Half material we received remaining supplier arrange in the material delivered by next week
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478 | 17.03.2021 | Pannel doors part 1 | Half of the material we received remaining we will pick up from SSLLP next week
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177491 | 18.03.2021 | Grills part 1 | No stock At supplier
177494 | 19.03.2021 | Sadara li Grey Granite | Half of the material we received remaining material supplier arrange the material delivered by next week
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Supplier arrange the material delivered by next week
177513 | 20.03.2021 | Cu multi wires ,tv ,spring wire | Half of the material we received remaining material supplier arrange the material delivered by next week
177514 | 20.03.2021 | Main door beeding | Supplier Arrange the Material delivered by next week
177541 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week SSLLP
177543 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week SSLLP
177544 | 31.03.2021 | Doors beeding | will pick up from SSLLP next week
177559 | 06.04.2021 | Luna ,ultra , Malaysian lt,dk, hl | Half of the material we received remaining material supplier arrange the material delivered by next week
177560 | 06.04.2021 | Classic dyna | Half of the material we received remaining material supplier arrange the material delivered by next week
177561 | 06.04.2021 | Traventine Romano | Supplier Arrange the Material delivered by next week
177562 | 06.04.2021 | Vitrified tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177563 | 06.04.2021 | Kitchen dado,utility floor tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177564 | 06.04.2021 | Ms Railing | No stock At supplier
177574 | 12.04.2021 | Z angle templates | Half of the material we received remaining supplier arrange the material delivered by next week
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Supplier arrange the material delivered by next week
177583 | 17.04.2021 | Pvc pipes | Half of the material we received remaining we will pick up from SSLLP next week
177591 | 20.04.2021 | AMC for Generator Set | Work under progress
177597 | 23.04.2021 | Bath room tiles | Half of the material we received remaining we will pick up from SSLLP next week
177599 | 24.04.2021 | Grigio serena, concrete beige & concrete grigio | Half of the material we received remaining we will pick up from GMR site
177628 | 04.05.2021 | Blue sheet covers | Material is Ready We will pick up from SSLLP Next week
177630 | 04.05.2021 | MS grills | No stock At supplier
177636 | 06.05.2021 | Texture | Supplier Arrange the material delivered by next week
177637 | 06.05.2021 | CP sq jalli | half of the material we received remaining we will pick up from SSLLP next week
177639 | 06.05.2021 | Plasticizer | lf of the material we received remaining we will pick up from SSLLP next week